## Summary
Module | Phase | Sprint(s) | Stories | Done | Working | Ready | Sprint Complexity | Duration (wks) | Surfaces
UI/UX Design — Mobile | Phase 0 — Foundation | S1-S2 | 7 | 0 | 0 | 7 | Very High | 4 | iOS, Android, Web, Admin
UI/UX Design — Web & Admin | Phase 0 — Foundation | S2-S3 | 6 | 0 | 0 | 6 | High | 4 | iOS, Android, Web, Admin
Architecture & Tech Stack | Phase 0 — Foundation | S1 | 4 | 0 | 0 | 4 | High | 2 | iOS, Android, Web, Admin, Backend
Database Schema & Data Model | Phase 0 — Foundation | S2 | 5 | 0 | 0 | 5 | High | 2 | Backend
API Contract & Integration Map | Phase 0 — Foundation | S3 | 4 | 0 | 0 | 4 | High | 2 | iOS, Android, Web, Admin, Backend
Project Setup & CI/CD | Phase 0 — Foundation | S1-S3 | 5 | 0 | 0 | 5 | High | 6 | iOS, Android, Web, Admin, Backend
Auth, Identity & RBAC | Phase 0 — Foundation | S3-S4 | 8 | 0 | 0 | 8 | High | 4 | iOS, Android, Web, Admin, Backend
Discovery & Open Items | Phase 0 — Foundation | S1-S3 | 1 | 0 | 0 | 1 | Medium | 6 | iOS, Android, Web, Admin, Backend
Home & Panchang | Phase 1 — v1.0 (initial launch) | S4 | 6 | 0 | 0 | 6 | Medium | 2 | iOS, Android, Web, Admin, Backend
Calendar & Events | Phase 1 — v1.0 (initial launch) | S5 | 6 | 0 | 0 | 6 | Medium | 2 | iOS, Android, Web, Admin, Backend
Content & Newsletter | Phase 1 — v1.0 (initial launch) | S5 | 6 | 0 | 0 | 6 | Medium | 2 | iOS, Android, Web, Admin, Backend
Payments & Billing Infrastructure | Phase 1 — v1.0 (initial launch) | S6 | 6 | 0 | 0 | 6 | Very High | 2 | iOS, Android, Web, Admin, Backend
Admin — Shell, Dashboards & Members | Phase 1 — v1.0 (initial launch) | S6-S7 | 7 | 0 | 0 | 7 | High | 4 | Admin, Backend
Donations & Causes | Phase 1 — v1.0 (initial launch) | S7 | 6 | 0 | 0 | 6 | High | 2 | iOS, Android, Web, Admin, Backend
Recurring Giving & Subscriptions | Phase 1 — v1.0 (initial launch) | S8 | 5 | 0 | 0 | 5 | High | 2 | iOS, Android, Web, Admin, Backend
Membership, Family & Dues | Phase 1 — v1.0 (initial launch) | S8 | 6 | 0 | 0 | 6 | High | 2 | iOS, Android, Web, Admin, Backend
Sponsorships & Religious Calendar | Phase 1 — v1.0 (initial launch) | S9 | 6 | 0 | 0 | 6 | High | 2 | iOS, Android, Web, Admin, Backend
Community Feed & Moderation | Phase 1 — v1.0 (initial launch) | S10 | 6 | 0 | 0 | 6 | Medium | 2 | iOS, Android, Web, Admin, Backend
Notifications & Messaging | Phase 1 — v1.0 (initial launch) | S11 | 6 | 0 | 0 | 6 | High | 2 | iOS, Android, Web, Admin, Backend
Pathshala | Phase 1 — v1.0 (initial launch) | S12 | 4 | 0 | 0 | 4 | Medium | 2 | iOS, Android, Web, Admin, Backend
Volunteers & Seva | Phase 1 — v1.0 (initial launch) | S12 | 4 | 0 | 0 | 4 | Medium | 2 | iOS, Android, Web, Admin, Backend
Live Darshan | Phase 1 — v1.0 (initial launch) | S13 | 5 | 0 | 0 | 5 | Very High | 2 | iOS, Android, Web, Admin, Backend
Admin — Governance & Operations | Phase 1 — v1.0 (initial launch) | S13 | 8 | 0 | 0 | 8 | High | 2 | iOS, Android, Web, Admin, Backend
Public Web & SEO | Phase 1 — v1.0 (initial launch) | S14 | 4 | 0 | 0 | 4 | Medium | 2 | Web, Backend
Localization & Accessibility | Phase 1 — v1.0 (initial launch) | S15 | 5 | 0 | 0 | 5 | Medium | 2 | iOS, Android, Web, Admin, Backend
Security, Testing & QA | Phase 1 — v1.0 (initial launch) | S16-S17 | 6 | 0 | 0 | 6 | High | 4 | iOS, Android, Web, Admin, Backend
Store & Launch Readiness | Phase 1 — v1.0 (initial launch) | S18-S19 | 5 | 0 | 0 | 5 | High | 4 | iOS, Android, Web, Admin
Governance & Documents | Phase 2 — v1.5 (should-have follow-on release) | S20 | 4 | 0 | 0 | 4 | Medium | 2 | iOS, Android, Web, Admin, Backend
Library, Jinvani & Lectures | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 | 6 | 0 | 0 | 6 | High | 4 | iOS, Android, Web, Admin, Backend
Directory, Travel & Facility Booking | Phase 2 — v1.5 (should-have follow-on release) | S23 | 5 | 0 | 0 | 5 | Medium | 2 | iOS, Android, Web, Admin, Backend
Recognition Programs | Phase 2 — v1.5 (should-have follow-on release) | S24 | 4 | 0 | 0 | 4 | Medium | 2 | iOS, Android, Web, Admin, Backend
Youth & YJA | Phase 2 — v1.5 (should-have follow-on release) | S24 | 3 | 0 | 0 | 3 | Medium | 2 | iOS, Android, Web, Admin, Backend
Past Events & Gallery | Phase 2 — v1.5 (should-have follow-on release) | S25 | 3 | 0 | 0 | 3 | Medium | 2 | iOS, Android, Web, Admin, Backend
Reports & Analytics v2 | Phase 2 — v1.5 (should-have follow-on release) | S25 | 3 | 0 | 0 | 3 | Medium | 2 | Admin, Backend
Hindi & Gujarati Localization | Phase 2 — v1.5 (should-have follow-on release) | S26 | 3 | 0 | 0 | 3 | Medium | 2 | iOS, Android, Web, Admin, Backend
v1.5 Hardening & Release | Phase 2 — v1.5 (should-have follow-on release) | S27 | 3 | 0 | 0 | 3 | High | 2 | iOS, Android, Web, Admin, Backend
Jain Philosophy Module | Phase 3 — v2.0 (nice-to-have and contingent) | S28-S29 | 3 | 0 | 0 | 3 | Medium | 4 | iOS, Android, Web, Admin, Backend
JCA Cares | Phase 3 — v2.0 (nice-to-have and contingent) | S30 | 2 | 0 | 0 | 2 | Low | 2 | iOS, Android, Web, Admin, Backend
v2.0 Hardening & Release | Phase 3 — v2.0 (nice-to-have and contingent) | S31 | 2 | 0 | 0 | 2 | Medium | 2 | iOS, Android, Web, Admin, Backend
AI Chat (contingent workstream) | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 | 5 | 0 | 0 | 5 | Very High | 3 | iOS, Android, Web, Admin, Backend
TOTAL |  |  | 193 | 0 | 0 | 193 |  | 105
Team shape: 6-8 people (1 PM/BA, 1 designer, 2 backend, 2 web/admin, 2 React Native, 1 QA), parallel surface tracks. Cadence: 2-week sprints, relative labelling.
Sprint numbers and week ranges below assume a 6-8 person team running fully parallel surface tracks from Sprint 1. A 3-4 person team cannot run design, backend, web, and mobile in parallel with the same depth: expect Phase 1 to extend from ~19 sprints to ~30-32 sprints (modules become mostly sequential, one or two in flight at a time). A 10-12 person team with a dedicated admin-utility pod can compress Phase 1 to ~14-15 sprints, but coordination overhead and design-review turnaround become the new bottleneck rather than raw implementation capacity.

## Phase & Sprint Roadmap
Sprint | Phase | Weeks | Modules in Flight | Sprint Goal | Complexity | Gate / Demo
Phase 0 — Foundation — Sprints 1–3, Weeks 1–6
Discovery resolved, design system locked, skeletons deployed, auth working — gates all feature work per RFP §4.1.1.
S1 | Phase 0 | Weeks 1–2 | UI/UX Design — Mobile, Architecture & Tech Stack, Project Setup & CI/CD, Discovery & Open Items | Kick off design-token extraction, ratify the stack, stand up five empty repos with CI, open every Discovery question. | High | Internal — repo + CI skeleton demo to JCA project committee
S2 | Phase 0 | Weeks 3–4 | UI/UX Design — Mobile, UI/UX Design — Web & Admin, Database Schema & Data Model, Project Setup & CI/CD, Discovery & Open Items | Lock mobile screens in Figma with the corrected palette; begin web/admin derivation; first schema pass; audit the existing DB JCA mentioned. | Very High | Design review — 28 mobile screens + palette-conflict resolution memo
S3 | Phase 0 | Weeks 5–6 | UI/UX Design — Web & Admin, API Contract & Integration Map, Project Setup & CI/CD, Auth, Identity & RBAC, Discovery & Open Items | Publish the OpenAPI contract, close all seven RFP §4.6 Discovery items, land Sign in with Apple/Google end-to-end. | High | Phase 0 exit gate — Discovery report + design system + API contract, per RFP §6.1.1 item 1
Phase 1 — v1.0 (initial launch) — Sprints 4–19, Weeks 7–38
Every P1 feature live on iOS, Android, Web, and Admin. App Store + Play Store approved. Public web launched. RFP §4.1.
S4 | Phase 1 | Weeks 7–8 | Home & Panchang, Auth, Identity & RBAC | Home dashboard and Panchang live end-to-end on all three member surfaces; auth hardened. | Medium | Sprint demo
S5 | Phase 1 | Weeks 9–10 | Calendar & Events, Content & Newsletter | Month-grid calendar, event detail + RSVP, and admin-authored announcements/content shipping. | Medium | Sprint demo
S6 | Phase 1 | Weeks 11–12 | Payments & Billing Infrastructure, Admin — Shell, Dashboards & Members | Stripe + PayPal wired with webhooks and idempotency; admin shell with Member 360 view online. | Very High | Sprint demo — first real charge in staging
S7 | Phase 1 | Weeks 13–14 | Donations & Causes, Admin — Shell, Dashboards & Members | Causes list, quick-give, event-based prioritization, and Jeev Daya live; admin bulk import complete. | High | Sprint demo
S8 | Phase 1 | Weeks 15–16 | Recurring Giving & Subscriptions, Membership, Family & Dues | Recurring giving with 2-tap pause/edit/cancel; family records and pending-dues card with Pay All Now. | High | Sprint demo
S9 | Phase 1 | Weeks 17–18 | Sponsorships & Religious Calendar | Sponsor a Tithi, five-tradition Daily Pooja & Abhishek schedule, Bhojanshala kitchen calendar, Sponsors of the Month. | High | Sprint demo
S10 | Phase 1 | Weeks 19–20 | Community Feed & Moderation | Whitelist-first community feed with author-only pending state; admin moderation queue with presence indicators. | Medium | Sprint demo
S11 | Phase 1 | Weeks 21–22 | Notifications & Messaging | APNs/FCM/Web Push/email fan-out live; notification composer with multi-surface preview and segment builder. | High | Sprint demo
S12 | Phase 1 | Weeks 23–24 | Pathshala, Volunteers & Seva | Children's class hub and volunteer sign-up/hour-logging live on all surfaces. | Medium | Sprint demo
S13 | Phase 1 | Weeks 25–26 | Live Darshan, Admin — Governance & Operations | Five-tradition HLS player with PiP/AirPlay/Cast; audit log, two-person confirmation, soft-delete trash, feature flags. | Very High | Sprint demo
S14 | Phase 1 | Weeks 27–28 | Public Web & SEO | Public information pages indexable, structured data, sitemap/robots, unauthenticated donate + newsletter signup. | Medium | Sprint demo
S15 | Phase 1 | Weeks 29–30 | Localization & Accessibility | Shared translation catalog wired end-to-end; English fully populated; per-surface accessibility audit closed. | Medium | Sprint demo
S16 | Phase 1 | Weeks 31–32 | Security, Testing & QA | ≥70% business-logic coverage; E2E suite for the five critical flows; dependency scanning in CI. | High | Sprint demo — coverage report
S17 | Phase 1 | Weeks 33–34 | Security, Testing & QA | Third-party penetration test executed; remediation of High/Critical findings in progress. | High | Pen-test report delivered
S18 | Phase 1 | Weeks 35–36 | Store & Launch Readiness | Store submission packages assembled; TestFlight + Play Internal Testing distribution; pen-test remediation closed. | Medium | TestFlight / Internal Testing build available to JCA committee
S19 | Phase 1 | Weeks 37–38 | Store & Launch Readiness | App Store and Google Play approval; public web and admin utility in production. | High | Phase 1 acceptance gate — RFP §6.2, all four surfaces live
Phase 2 — v1.5 (should-have follow-on) — Sprints 20–27, Weeks 39–54
Member-gated content, governance transparency, richer educational resources. Hindi/Gujarati fully populated. RFP §4.2.
S20 | Phase 2 | Weeks 39–40 | Governance & Documents | Meeting minutes archive (gated, searchable, PDF), JCA Policies, Credits & History. | Medium | Sprint demo
S21 | Phase 2 | Weeks 41–42 | Library, Jinvani & Lectures | Scripture/lecture catalog with continue-reading state; Meilisearch stood up for full-text PDF search. | High | Sprint demo
S22 | Phase 2 | Weeks 43–44 | Library, Jinvani & Lectures | Pathshala Books digital library with grade-level browse and parental controls; offline audio download. | Medium | Sprint demo
S23 | Phase 2 | Weeks 45–46 | Directory, Travel & Facility Booking | Business Directory, Restaurants, Jain Centers USA, and Facility Booking with deposit tracking and conflict view. | Medium | Sprint demo
S24 | Phase 2 | Weeks 47–48 | Recognition Programs, Youth & YJA | Service Awards nomination flow, Lifetime Supporter Program, Youth section with age-gating. | Medium | Sprint demo
S25 | Phase 2 | Weeks 49–50 | Past Events & Gallery, Reports & Analytics v2 | Auto-generated Past Events archive; expanded admin reporting (cohort, retention, dues-aging trend). | Medium | Sprint demo
S26 | Phase 2 | Weeks 51–52 | Hindi & Gujarati Localization | Full Hindi and Gujarati translation populated across all surfaces with reviewer workflow. | Medium | Sprint demo
S27 | Phase 2 | Weeks 53–54 | v1.5 Hardening & Release | Pen-test refresh for the v1.5 surface area; store updates submitted and approved. | High | Phase 2 acceptance gate — RFP §6.1.2
Phase 3 — v2.0 (nice-to-have, contingent) — Sprints 28–31 (+ parallel AI Chat workstream), Weeks 55–62 (+10 wks AI Chat)
Educational depth and intelligent assistance. Contingent on Phase 1 and Phase 2 acceptance gates. RFP §4.3.
S28 | Phase 3 | Weeks 55–56 | Jain Philosophy Module | Curriculum structure for anekantvad, ahimsa, syadvad, Nine Tattvas; lesson authoring tools. | Medium | Sprint demo
S29 | Phase 3 | Weeks 57–58 | Jain Philosophy Module | Progress tracking across the Five Mahavratas and Twelve Vratas modules; full curriculum live. | Medium | Sprint demo
S30 | Phase 3 | Weeks 59–60 | JCA Cares | Charitable-campaign management integrated with the Causes module for disaster relief and outreach. | Low | Sprint demo
S31 | Phase 3 | Weeks 61–62 | v2.0 Hardening & Release | Regression pass, updated pen-test scope, store updates for the v2.0 surface area. | Medium | Phase 3 acceptance gate — RFP §6.1.3 (excluding AI Chat)
AI-1 | Phase 3 | AI Chat Wk 1–2 (parallel to S28-S29) | AI Chat (contingent workstream) | Knowledge-base ingestion pipeline for JCA institutional content; retrieval architecture spike. | High | Internal — architecture review
AI-2 | Phase 3 | AI Chat Wk 3–4 | AI Chat (contingent workstream) | Guardrail design: doctrine-deferral rules, source citation, escalation triggers. | Very High | Internal — guardrail review with JCA religious advisors
AI-3 | Phase 3 | AI Chat Wk 5–6 | AI Chat (contingent workstream) | Chat UI on mobile + web; escalation-to-human-staff queue in the admin utility. | High | Sprint demo
AI-4 | Phase 3 | AI Chat Wk 7–8 | AI Chat (contingent workstream) | Response audit tooling; user-feedback loop; knowledge-base curation UI for admins. | Medium | Sprint demo
AI-5 | Phase 3 | AI Chat Wk 9–10 | AI Chat (contingent workstream) | Closed pilot with committee members; guardrail tuning; go/no-go for general release. | Medium | AI Chat acceptance gate — separate commission per RFP §6.1.3 item 19

## Tech Decisions
Decision | Fixed by User | Options Considered | Offense (case for) | Defence (risk / case against) | Recommendation | Blocks Sprint
Web framework (public web) | No | Next.js 15 (App Router) · Remix · SvelteKit · plain Vite SPA | SEO is a hard RFP requirement (§4.1.3, §5.4: meta tags, structured data, sitemap, robots.txt, canonical URLs). Next.js gives SSR + ISR out of the box, server components cut JS payload for elders on older phones, and one app serves both the public site and the signed-in member dashboard described in §3.2 as "a web mirror of the mobile experience." | App Router has real learning-curve cost and a history of breaking changes; deploying on Vercel risks vendor lock-in — mitigated by containerizing with `next start` behind our own reverse proxy on Cloud Run rather than depending on Vercel's platform. A plain Vite SPA is rejected outright: it cannot satisfy the SEO requirement without a separate prerendering layer that duplicates Next.js's job. | Next.js 15, App Router, self-hosted on Cloud Run | S1
Admin utility frontend | No | Next.js route group inside the public web app · Separate Vite + React SPA | The admin utility has no SEO need and a completely different UX register — dense tables, a ⌘K command palette, keyboard shortcuts (§4.4.1). A separate Vite SPA gets a faster dev loop, ships to its own subdomain (admin.nyjaincenter.org per §5.4) with independent MFA and optional IP allowlisting, and guarantees admin-only code never leaks into the public bundle members and search engines see. | Two frontend codebases instead of one means duplicated setup and a second build pipeline. Mitigated by sharing `packages/ui` and `packages/tokens` across both apps in the monorepo, so components and design tokens are written once. | Separate Vite + React SPA, deployed independently | S1
Mobile framework | Yes | React Native (Expo, dev client + EAS Build) · React Native (bare workflow) | User has fixed React Native so one codebase covers iOS 17+ and Android 12+ (API 31) without maintaining two native builds, per RFP §1 requirement for feature parity. Expo's managed workflow plus a custom dev client gives config plugins for native modules while keeping EAS Build/Submit for both stores from one pipeline. `expo-updates` can ship copy and content fixes without a store review cycle — real value for a volunteer-run nonprofit that cannot wait a week for an App Store review to fix a typo in a festival date. | Live Darshan requires Picture-in-Picture, AirPlay, and Google Cast (§4.1.2). `react-native-video` v6 and `react-native-google-cast` ship config plugins but require a custom dev client, not Expo Go — meaning the team cannot use the vanilla Expo Go app for daily testing. **Mitigation:** booked as an explicit spike in Sprint 1 (Architecture & Tech Stack) to prove the dev-client build before any feature work depends on it. | Expo (managed workflow, custom dev client) + EAS Build/Submit | S1
Backend framework | No | Django 5 + Django REST Framework · FastAPI + SQLAlchemy · Node.js/TypeScript · Go | User has fixed Python; this decision is framework-within-Python. The system is CRUD-and-workflow heavy across ~75 tables and 20 admin sections (§3.4), not compute-heavy. Django's ORM + migrations, built-in auth, and a granular permission model give most of the admin utility's RBAC requirement (§4.4.1) for free. `django-simple-history` covers the immutable 7-year audit log; `django-safedelete` covers the 30-day soft-delete/tombstone requirement; `django-allauth` covers Sign in with Apple/Google. Celery (with the same Postgres-backed broker) handles push fan-out, scheduled publish, and dues-reminder dunning. | DRF serializers are more verbose than FastAPI's Pydantic models, and Django's async story is weaker than FastAPI's native async. This is a real cost on any endpoint that fans out to multiple third-party APIs concurrently (e.g. multi-channel notification delivery) — mitigated by running those specific paths as Celery tasks rather than in-request async code. FastAPI remains the better choice for the Phase 3 AI Chat service, which is a genuinely different, streaming-heavy workload — RFP §4.3 already anticipates a "substantially different technology stack" for that workstream. | Django 5 + DRF + drf-spectacular for the core platform; FastAPI reserved for the standalone AI Chat service | S1
Primary database | No | PostgreSQL 16 · MySQL 8 · migrate/extend JCA's existing database | Relational integrity is non-negotiable for money and membership data. Postgres adds JSONB for flexible content blocks (event schedules, quiz questions), `pg_trgm` + `unaccent` for typo-tolerant, diacritic- aware search over Sanskrit/Prakrit terms (§4.4.1), and row-level audit triggers that back the immutable audit log. | RFP §1.1 states a database is "already available," and §3.4 item 15 says "the database of library books is already available." We do not yet know what that system is. **Mitigation:** a dedicated audit and migration-path story is booked in Sprint 2 (Database Schema & Data Model) before the schema is frozen, so existing data is assessed before Postgres is committed to as the system of record. | PostgreSQL 16, pending the Sprint 2 legacy-database audit | S2
Payment processor | No | Stripe + PayPal Commerce · Stripe only · Authorize.net · Donorbox/Givebutter hosted widgets | Stripe covers cards, Apple Pay, Google Pay, ACH, and Stripe Billing for recurring giving with pause/edit/cancel in two interactions or fewer (§2.2). Payment Element (web) and the Stripe React Native SDK keep the platform at PCI SAQ-A — card numbers never touch our servers. The Refunds API is idempotent, which fits the two-person-confirmation rule for money (§4.4.1) cleanly: one admin initiates, the second confirms, then the refund call fires once. Stripe offers a reduced processing rate for registered 501(c)(3) nonprofits. | Stripe's own PayPal payment method is not available to US-based Stripe accounts, but §4.1.3 explicitly requires PayPal support — so Stripe alone does not satisfy the RFP. PayPal Commerce Platform is integrated as a second, separate rail specifically for that requirement. **Rejected:** Authorize.net has no clean native-wallet (Apple Pay/Google Pay) story for React Native. Donorbox/Givebutter are rejected because their hosted-widget model can't be embedded natively inside a React Native donation flow and would fork receipts and donation records outside our single source of truth (§2.2). Receipts are generated by our own backend, not by the processor — 501(c)(3) receipts must carry JCA's EIN and "no goods or services were provided" language, which is JCA-specific content no processor template provides. Zelle/bank transfer shown in the mockup is treated as off-platform and recorded via the admin's manual donation-entry component, not as a live payment rail. | Stripe (cards, Apple Pay, Google Pay, ACH, Billing) as primary; PayPal Commerce Platform as secondary rail | S6
Search | No | PostgreSQL full-text search + pg_trgm + unaccent · Elasticsearch · Meilisearch (from day one) · Algolia | §4.4.1 requires typo-tolerant search across members, families, donations, events, and posts, including Sanskrit/Prakrit terminology and name transliterations. Postgres FTS with `pg_trgm` (trigram similarity) and `unaccent` (diacritic-insensitive matching) covers this without standing up a second datastore, which keeps Phase 1 infrastructure simpler and the audit surface smaller. | Full-text search over scanned/OCR'd PDF scripture and lecture content in the Phase 2 Library & Jinvani module is exactly the workload Postgres FTS starts to strain under — ranking quality and multi-language stemming are weaker than a dedicated search engine. **Mitigation:** Meilisearch is introduced in Sprint 21, precisely when that workload appears, rather than paying its operational cost from day one for admin/member search Postgres already handles well. | Postgres FTS + pg_trgm + unaccent in Phase 1; add Meilisearch in Phase 2 for library/lecture full-text search | S2
Cloud hosting | No | GCP (Cloud Run + Cloud SQL + Cloud Storage/CDN) · AWS (ECS/Fargate + RDS + S3/CloudFront) | Google for Nonprofits offers substantial Cloud credit grants to registered 501(c)(3) organizations — directly relevant to JCA's budget as a nonprofit. Cloud Run's scale-to-zero model suits a congregation-sized traffic pattern with sharp peaks around festivals (Paryushan, Diwali, MJK) and otherwise-quiet weekdays. Cloud Build gives a native CI/CD path matching the team's existing GCP experience. | Cloud Run cold starts add latency on the first request after an idle period — mitigated with a minimum-instance-count of 1 on the API service so the admin utility and payment endpoints never cold-start. AWS ECS/Fargate + RDS + S3/CloudFront is recorded as the equivalent alternative if JCA's board has an existing AWS relationship or credit commitment; the Terraform/IaC layer is written to keep this swap feasible without an application-code rewrite. | GCP — Cloud Run, Cloud SQL (Postgres), Cloud Storage + Cloud CDN, Secret Manager, Cloud Build | S1
Live Darshan streaming | No | Player only, JCA-supplied HLS URLs · Fully managed live encoding (Mux / Cloudflare Stream Live) | RFP §3.4 item 14 scopes the admin's job as configuring stream-source URLs per tradition (HLS URLs, fallback, scheduled on/off windows) and monitoring stream health — not operating an encoder. Building only the player, PiP, AirPlay/Cast, and health-check layer keeps several sprints of encoding infrastructure out of scope that the RFP never asked for. | If JCA does not already have a hardware or software encoder producing HLS streams from the five shrines, this decision assumes infrastructure that may not exist. **Mitigation:** this is flagged as a Discovery question (see Discovery & Open Items) — if JCA has no encoder, a managed live-encoding service becomes a separately-priced change order, not silent scope creep absorbed into Phase 1. | Player only in Phase 1; managed encoding is a change order if Discovery reveals JCA has no encoder | S1
Monorepo tooling | No | Turborepo + pnpm workspaces · Nx · separate repos per surface | RFP §3.1 requires all four surfaces to share the same design tokens (colors, typography, spacing, radii, shadows). A single `packages/tokens` source of truth — generating CSS custom properties for web/admin and a React Native theme object for mobile from the same token file — satisfies that requirement structurally rather than by convention. A generated TypeScript API client from the OpenAPI schema in `packages/api-client` eliminates drift between backend contract and frontend usage across three separate frontend codebases. | EAS Build needs explicit configuration to build a mobile app that lives inside a monorepo rather than at a repo root — this is booked as a named subtask in Project Setup & CI/CD (Sprint 1) rather than discovered mid-Phase-1. | Turborepo + pnpm workspaces: apps/web, apps/admin, apps/mobile, packages/tokens, packages/api-client, packages/validation; backend in services/api | S1
Localization approach | No | Centralized translation catalog in the backend · Per-surface translation files (i18next/next-intl per app, duplicated) | RFP §3.1 explicitly requires localization to be centralized — "strings live in the backend or a shared catalog, not duplicated per surface." A `localization_string` table with a key/locale/value shape, served through the API and cached on each client, gives the admin utility's translator-review workflow (§5.2) a single place to manage English, Hindi, and Gujarati content rather than three. | A backend-served catalog adds a network dependency for strings that per-surface i18next files would resolve at build time — mitigated by aggressive client-side caching of the catalog with a version/ETag check, so steady-state usage never re-fetches unchanged strings. | Centralized localization_string table, served via API, cached per client with version-checked invalidation | S3

## Discovery & Open Items
ID | Item | Source | Open Question | Recommendation | Owner | Resolve By
DISC-1 | Education — module boundary | RFP §4.6 | Is Education a top-level module distinct from Pathshala, Jain Philosophy, and Lectures, or a wrapper/umbrella around them? | Treat as a wrapper: an 'Education' entry point in the More grid that surfaces Pathshala, Jain Philosophy (Phase 3), and Lectures as sub-destinations, rather than a fourth parallel content system. | JCA project committee + Vendor IA lead | S2
DISC-2 | Religious activities — synonym or separate module? | RFP §4.6 | Is 'Religious activities' a synonym for Events / Cultural / Daily Pooja & Abhishek, or a separate module? Treated as P1 pending Discovery. | Fold into the existing Events category taxonomy (Religious / Cultural / Educational, per §3.4 item 3) rather than building a parallel module — avoids duplicate calendar surfaces. | JCA project committee | S1
DISC-3 | Restoration — active campaign? | RFP §4.6 | Is Restoration an active fundraising campaign? If so, integrate as an event-based Donate cause. | If confirmed active, model as a standard Cause with an optional linked Event, using the existing event-based goal-prioritization mechanism — no new donation type needed. | JCA Treasurer / Donations chair | S2
DISC-4 | MFA scope | RFP §4.6, §4.1.3 | MFA priority is unmarked. Confirm mandatory for Admin, optional for members. | Admin utility: MFA mandatory at first login, no bypass. Member surfaces: MFA optional, offered at signup and configurable per role in Profile > Settings. | JCA project committee (security posture sign-off) | S3
DISC-5 | Private Events Information — gating rule | RFP §4.6 (P2) | Confirm membership-gating rule: tier-based, family-role-based, or committee-based? | Tier-based as the default rule (matches the existing Membership tier model everywhere else); family-role and committee-based overrides available per-event via the Event editor's existing sponsorship-tier pattern. | JCA Events chair | S20 (Phase 2 kickoff)
DISC-6 | Skip to Content — accessibility equivalent | RFP §4.6 (P2) | Propose the platform-native accessibility equivalent per surface. | iOS: VoiceOver rotor with landmark navigation. Android: TalkBack heading/landmark navigation. Web: a visually-hidden, focus-visible 'Skip to main content' link as the first focusable element on every page. | Vendor accessibility lead | S3
DISC-7 | Youth — scope distinct from Pathshala and YJA | RFP §4.6 (P2) | Confirm scope distinct from Pathshala (under 18) and YJA Programs (18-25); confirm whether age-gating is required. | Youth = ages 13-25, overlapping the top of Pathshala and the start of YJA by design (per the walkthrough's stated 13-25 range) — age-gating required for youth-specific social/mentorship content, self-attested at signup with parental consent under 18. | JCA project committee | S24 (Phase 2, Youth & YJA sprint)
DISC-8 | Design-system palette conflict — crimson/gold vs. indigo/saffron | Vendor review of source materials, not in RFP text | jca-ny-app_vSHARE.html uses crimson/gold/cream (RFP §2.2-compliant: 'never saffron/orange'). jca-app-mockup.html and the entire admin mockup use indigo/saffron. The walkthrough deck also references 'calm indigo + saffron.' Which is authoritative? | vSHARE (crimson/gold) is authoritative per explicit RFP text. The indigo/saffron admin mockup and jca-app-mockup.html are superseded design-exploration artifacts. Admin visual language is re-derived from the vSHARE tokens in Sprint 2-3, not carried forward as-is. | JCA project committee (design sign-off required per RFP §2.3) | S1
DISC-9 | Legacy database — scope and migration path | RFP §1.1 ('Existing database already available'), §3.4 item 15 (library-book DB) | What system currently holds member/donation data (if any) and the library-book catalog? What is its schema, size, and export format? | Full audit and migration-path proposal delivered before the Sprint 2 schema is frozen. If no meaningful existing member database is found beyond the library catalog, treat the library-book DB as the only real migration source and design a one-time ETL into the new schema. | Vendor backend lead + JCA IT contact | S2
DISC-10 | Design-system contrast failure — gold on cream | Vendor accessibility review of vSHARE tokens, not in RFP text | RFP §2.2 mandates WCAG 2.1 AA everywhere. Measured: --gold #c9a961 on --cream #faf6ef = 2.09:1 (fail); --gold-deep #8c6f30 on --cream = 4.40:1 (fails AA body text by a narrow margin, passes large text only). How should gold be used to stay both on-brand and compliant? | Adopt a corrected token set: gold restricted to ornamental use (borders, icons, dividers, large display type ≥24px) never body text; introduce an AA-safe '--gold-text' (~#7d6229, 5.5:1+ on cream) for any place gold-colored text is needed. Documented as a hard rule in the design system, not a per-screen judgment call. | Vendor design lead | S1

## DB Schema
Domain | Table | Purpose | Key Columns | Foreign Keys | Phase
Identity & Access | user | One record per real person — the single source of identity RFP §3.1 requires. | email, phone, display_name, preferred_locale, status | — | phase0
Identity & Access | auth_identity | Linked external identity per sign-in method (Apple, Google, email/password). | provider, provider_subject_id, user_id | user_id -> user | phase0
Identity & Access | mfa_factor | Registered MFA factors — mandatory for admin, optional for members. | user_id, factor_type, secret_ref, verified_at | user_id -> user | phase0
Identity & Access | role | The role catalog: Guest, Member, Family Primary, Pathshala Parent, Committee Member, Admin, Super-Admin, plus any Vendor-proposed additions. | name, description | — | phase0
Identity & Access | permission | Granular per-section permission catalog (read / write / approve / money) per admin section. | section, action | — | phase0
Identity & Access | role_permission | Role-to-permission grants, with per-record override support. | role_id, permission_id, scope_override | role_id -> role, permission_id -> permission | phase0
Identity & Access | user_role | User-to-role assignment, many-to-many (a Committee Member can also be a Family Primary). | user_id, role_id | user_id -> user, role_id -> role | phase0
Identity & Access | session | Active session per device/surface, backing HttpOnly/Secure/SameSite web cookies and mobile refresh tokens. | user_id, surface, device_info, expires_at, revoked_at | user_id -> user | phase0
Identity & Access | audit_log | Immutable, append-only log of every state-changing operation. Retained seven years. Never updated or deleted by application code. | actor_user_id, action_type, target_table, target_id, before_state, after_state, second_actor_user_id | actor_user_id -> user, second_actor_user_id -> user (nullable, two-person rule) | phase0
Membership | member_profile | Member-specific fields layered on user — member ID, gotra, tradition affiliation. | user_id, member_id, tradition_id, gotra, joined_date | user_id -> user, tradition_id -> tradition | phase0
Membership | tradition | The five Jain traditions housed at JCA — used everywhere equal-visibility is required (Live Darshan, Calendar, religious content). | name (Shvetambara Murtipujak, Shvetambara Sthanakvasi, Shvetambara Terapanthi, Digambar, Shrimad Rajchandra) | — | phase0
Membership | family | One family record grouping related members. | family_name, primary_member_id | primary_member_id -> member_profile | phase1
Membership | family_member | Individual within a family — includes non-user children too young to have accounts. | family_id, relationship, dob, gotra, has_user_account | family_id -> family, user_id -> user (nullable) | phase1
Membership | membership_tier | Tier catalog (e.g. Standard, Patron, Lifetime) with pricing and renewal rules. | name, annual_price, is_lifetime | — | phase1
Membership | membership | A member's current tier, since-date, and renewal date. | member_profile_id, tier_id, since_date, renewal_date, status | member_profile_id -> member_profile, tier_id -> membership_tier | phase1
Membership | dues_item | A single billable line (annual membership, MJK pass, Pathshala term fee). | family_id, item_type, description, amount, due_date | family_id -> family | phase1
Membership | dues_ledger_entry | Ledger of dues issued / paid / comped / waived / refunded, running balance. | dues_item_id, entry_type, amount, admin_actor_id, second_actor_id | dues_item_id -> dues_item, admin_actor_id -> user, second_actor_id -> user (nullable) | phase1
Giving | cause | A giving cause (General, Maintenance, Bhojanshala, Pathshala, Jeev Daya, Restoration if confirmed active). | name, description, goal_amount, raised_amount, is_active, linked_event_id | linked_event_id -> event (nullable, for event-based prioritization) | phase1
Giving | donation | A single donation transaction (one-time). | cause_id, donor_user_id, amount, is_anonymous, memorial_text, payment_transaction_id | cause_id -> cause, donor_user_id -> user (nullable if off-platform), payment_transaction_id -> payment_transaction | phase1
Giving | donation_allocation | Supports a donation split across multiple causes or an event-tied goal. | donation_id, cause_id, amount | donation_id -> donation, cause_id -> cause | phase1
Giving | recurring_subscription | A recurring giving plan — daily aarti dāna, monthly general fund, yearly Paryushan dāna. | user_id, cause_id, amount, frequency, next_charge_date, status, stripe_subscription_id | user_id -> user, cause_id -> cause | phase1
Giving | payment_method | Saved payment method reference — tokenized only, never a raw card number (PCI). | user_id, provider, provider_payment_method_id, brand, last4 | user_id -> user | phase1
Giving | payment_transaction | Provider-agnostic transaction record — one row per Stripe or PayPal charge attempt. | provider, provider_transaction_id, amount, currency, status, idempotency_key | payment_method_id -> payment_method (nullable) | phase1
Giving | refund | A refund against a payment_transaction — requires two admin actors per the money rule. | payment_transaction_id, amount, reason, initiating_actor_id, confirming_actor_id | payment_transaction_id -> payment_transaction, initiating_actor_id -> user, confirming_actor_id -> user | phase1
Giving | receipt | Generated 501(c)(3) tax receipt PDF for a donation, including JCA EIN and required disclosure language. | donation_id, pdf_url, issued_at | donation_id -> donation | phase1
Giving | year_end_statement | Consolidated annual giving statement per member, and institution-wide for admin reporting. | member_profile_id, tax_year, pdf_url, generated_at | member_profile_id -> member_profile | phase1
Sponsorship | sponsorship | A sponsorship record generalized across Tithi, Pooja/Abhishek, Bhojanshala, and event sponsorship. | sponsorship_type, target_id, donation_id, is_anonymous, memorial_text | donation_id -> donation | phase1
Sponsorship | tithi_slot | A sponsorable tithi date on the calendar, per the Sponsor a Tithi flow. | tithi_date, tier, is_available | — | phase1
Sponsorship | pooja_slot | Daily pooja/abhishek slot, per tradition, sponsorable. | date, tradition_id, slot_time, sponsor_id, is_open | tradition_id -> tradition, sponsor_id -> sponsorship (nullable) | phase1
Sponsorship | bhojanshala_slot | A kitchen-calendar date with meal-type tiers (full lunch, sweet box, snack seva). | date, meal_tier, sponsor_id, meal_count | sponsor_id -> sponsorship (nullable) | phase1
Sponsorship | event_sponsorship_tier | Sponsorship tiers configured per event (e.g. Gold/Silver/Bronze swamivatsalya). | event_id, tier_name, amount, slots_available | event_id -> event | phase1
Events & Facilities | event | Unified event schema — Religious, Cultural, and Educational categories all share this table. | title, category, description, hero_media_id, rsvp_cap, linked_cause_id | hero_media_id -> media_asset, linked_cause_id -> cause (nullable) | phase1
Events & Facilities | event_category | Category catalog (Religious / Cultural / Educational) — admin-managed. | name | — | phase1
Events & Facilities | event_schedule_block | A time block within an event's full schedule (e.g. abhishek at 9am, snatra puja at 11am). | event_id, start_time, end_time, label | event_id -> event | phase1
Events & Facilities | rsvp | A member's RSVP to an event, with waitlist support. | event_id, user_id, status (confirmed/waitlisted/cancelled), party_size | event_id -> event, user_id -> user | phase1
Events & Facilities | attendance | Day-of check-in record — supports member-ID scan, name search, and walk-in capture. | event_id, user_id (nullable for walk-ins), checked_in_at, checked_in_by | event_id -> event, user_id -> user (nullable), checked_in_by -> user | phase1
Events & Facilities | facility | A bookable facility (Main Hall, Upashray, Marble Lobby) with member-rate pricing. | name, capacity, member_rate, policy_text | — | phase1
Events & Facilities | facility_booking | A hall reservation with approval workflow and deposit tracking. | facility_id, requested_by, date, status, deposit_amount, deposit_paid | facility_id -> facility, requested_by -> user | phase1
Community | post | A community feed post — admin announcement (auto-published) or member post (gated by moderation). | author_id, body, status (pending/approved/declined), pinned | author_id -> user | phase1
Community | post_media | Media attachments on a post. | post_id, media_asset_id | post_id -> post, media_asset_id -> media_asset | phase1
Community | post_reaction | A reaction on a post. | post_id, user_id, reaction_type | post_id -> post, user_id -> user | phase1
Community | moderation_action | Audit trail of every moderation decision (approve/decline/edit/flag) — feeds the immutable audit log. | post_id, admin_actor_id, action, reason | post_id -> post, admin_actor_id -> user | phase1
Community | badge | Badge catalog (Youth, Pathshala) assignable to users, shown on posts and profiles. | name, description | — | phase1
Community | content_report | A member-submitted report against a post, routed to the moderation queue. | post_id, reported_by, reason, status | post_id -> post, reported_by -> user | phase1
Content | announcement | Admin-authored announcement — pinned in feed, pushed to notifications on publish. | title, body, publish_at, unpublish_at, segment_id | segment_id -> segment (nullable) | phase1
Content | thought_of_day | Home dashboard's Thought of the Day content, one per date. | date, text, source_attribution | — | phase1
Content | quiz_question | Daily quiz question bank. | question_text, choices, correct_choice_index, active_date | — | phase1
Content | quiz_attempt | A member's daily quiz attempt, feeding the streak counter. | user_id, quiz_question_id, is_correct, attempted_at | user_id -> user, quiz_question_id -> quiz_question | phase1
Content | news_article | Curated long-form article, distinct from the real-time community feed. | title, body, category, published_at | — | phase1
Content | newsletter_issue | A newsletter issue with archive support. | issue_number, title, body, sent_at | — | phase1
Content | page | Static/lightly-dynamic CMS page (About Us, Contact, Help) with version control. | slug, title, body, version | — | phase1
Content | faq | FAQ entries with a managed taxonomy. | category, question, answer, sort_order | — | phase1
Content | policy_doc | JCA Policies — authored, versioned, published (Phase 2). | title, body, version, published_at | — | phase2
Content | meeting_minute | Board / Executive Committee / General Body meeting minutes — gated, searchable, PDF (Phase 2). | meeting_type, meeting_date, pdf_url, gated | — | phase2
Content | media_asset | Uploaded media (image, PDF, audio) stored in Cloud Storage/CDN, referenced across many content types. | storage_url, mime_type, alt_text, uploaded_by | uploaded_by -> user | phase0
Education & Seva | pathshala_class | A Pathshala class with a term schedule and assigned teacher. | grade_level, term_id, teacher_user_id, schedule | teacher_user_id -> user | phase1
Education & Seva | enrollment | A child's enrollment in a Pathshala class, with term-fee status. | family_member_id, pathshala_class_id, term_fee_status | family_member_id -> family_member, pathshala_class_id -> pathshala_class | phase1
Education & Seva | lesson | A lesson published to a class, with materials. | pathshala_class_id, title, lesson_date | pathshala_class_id -> pathshala_class | phase1
Education & Seva | material | Downloadable material attached to a lesson. | lesson_id, media_asset_id | lesson_id -> lesson, media_asset_id -> media_asset | phase1
Education & Seva | volunteer_opportunity | An open volunteer opportunity (Bhojanshala, Pathshala, Festival, Setup/Cleanup). | title, category, commitment, date, capacity | — | phase1
Education & Seva | volunteer_signup | A member's sign-up for an opportunity. | volunteer_opportunity_id, user_id, status | volunteer_opportunity_id -> volunteer_opportunity, user_id -> user | phase1
Education & Seva | volunteer_hour_log | Admin-entered hour log in v1.0; member self-entry deferred to Phase 2 consideration per RFP §3.4 item 10. | user_id, hours, logged_by, activity_date | user_id -> user, logged_by -> user | phase1
Education & Seva | service_award | Service Awards Program — nominations, recipients, eligibility (Phase 2). | nominee_user_id, nominated_by, status, award_year | nominee_user_id -> user, nominated_by -> user | phase2
Platform Operations | notification_template | Reusable templates for receipts, dues reminders, RSVP confirmations, sign-in alerts. | name, channel, subject, body_template | — | phase1
Platform Operations | notification_campaign | A composed, scheduled push/email send. | template_id, segment_id, scheduled_at, sent_at, status | template_id -> notification_template, segment_id -> segment | phase1
Platform Operations | segment | A saved recipient segment built from filter criteria (tab, tradition, family role, Pathshala enrollment, tier). | name, filter_definition (jsonb) | — | phase1
Platform Operations | device_token | Registered push token per device (APNs/FCM/Web Push). | user_id, platform, token, active | user_id -> user | phase1
Platform Operations | delivery_receipt | Per-notification, per-surface delivery metrics (sent/delivered/opened/bounced/opted-out). | notification_campaign_id, user_id, channel, status | notification_campaign_id -> notification_campaign, user_id -> user | phase1
Platform Operations | notification_preference | Per-member, per-category notification opt-in/opt-out (includes birthday/anniversary opt-in per family member). | user_id, category, channel, enabled | user_id -> user | phase1
Platform Operations | feature_flag | Feature-flag console backing — staff/committee/percentage/full rollout stages. | key, rollout_stage, rollout_percentage | — | phase1
Platform Operations | localization_string | Centralized translation catalog — one row per key/locale, per RFP §3.1. | key, locale, value, reviewed_by | — | phase0
Platform Operations | integration_credential | Encrypted-at-rest vault entry for payment/push/email/streaming/SSO credentials — Super-Admin only. | provider, credential_ref (Secret Manager pointer), rotated_at | — | phase0
Platform Operations | tombstone | Central index of soft-deleted records across all tables, backing the 30-day trash/recovery UI. | table_name, record_id, deleted_by, deleted_at, purge_at | deleted_by -> user | phase0

## API to Table Map
Endpoint | Method | Tables Read | Tables Written | Surfaces | Min Role | Phase | Story ID
/api/v1/auth/sign-in | POST | user, auth_identity | session, audit_log | iOS, Android, Web | Guest | phase0 | AUTH-1
/api/v1/auth/register | POST | user | user, member_profile, family, family_member, audit_log | iOS, Android, Web | Guest | phase0 | AUTH-2
/api/v1/auth/mfa/enroll | POST | user | mfa_factor, audit_log | Admin, iOS, Android, Web | Member | phase0 | AUTH-4
/api/v1/admin/roles | GET, POST, PATCH | role, permission, role_permission | role, role_permission, audit_log | Admin | Super-Admin | phase0 | AUTH-6
/api/v1/panchang/today | GET | — (computed/configured, no dedicated table; source config only) | — | iOS, Android, Web | Guest | phase1 | HP-2
/api/v1/home/dashboard | GET | thought_of_day, quiz_question, event, post, member_profile | — | iOS, Android, Web | Guest | phase1 | HP-1
/api/v1/quiz/today/attempt | POST | quiz_question | quiz_attempt | iOS, Android, Web | Member | phase1 | HP-4
/api/v1/events | GET | event, event_category, event_schedule_block | — | iOS, Android, Web | Guest | phase1 | CAL-1
/api/v1/events/{id}/rsvp | POST, DELETE | event, rsvp | rsvp, audit_log | iOS, Android, Web | Member | phase1 | CAL-3
/api/v1/admin/events | GET, POST, PATCH, DELETE | event, event_schedule_block, event_sponsorship_tier | event, event_schedule_block, event_sponsorship_tier, audit_log, tombstone | Admin | Committee Member | phase1 | CAL-4
/api/v1/admin/calendar/conflicts | GET | event, pooja_slot, facility_booking | — | Admin | Committee Member | phase1 | CAL-5
/api/v1/admin/content/announcements | GET, POST, PATCH | announcement, segment | announcement, notification_campaign, audit_log | Admin | Committee Member | phase1 | CN-1
/api/v1/newsletter/subscribe | POST | — | localization_string (n/a), segment (subscriber list) | Web | Guest | phase1 | CN-6
/api/v1/payments/intent | POST | payment_method | payment_transaction, audit_log | iOS, Android, Web | Guest | phase1 | PAY-1
/api/v1/payments/paypal/order | POST | — | payment_transaction, audit_log | iOS, Android, Web | Guest | phase1 | PAY-2
/api/v1/admin/refunds | POST | payment_transaction | refund, audit_log | Admin | Admin (money permission, two-actor) | phase1 | PAY-6
/api/v1/receipts/{donation_id} | GET | donation, receipt | receipt (on first generation) | iOS, Android, Web | Member | phase1 | PAY-5
/api/v1/admin/members/{id}/360 | GET | member_profile, family, membership, dues_ledger_entry, donation, volunteer_hour_log, enrollment, rsvp, post, session | — | Admin | Committee Member | phase1 | ADM-4
/api/v1/admin/members/import | POST | — | user, member_profile, family, family_member, audit_log | Admin | Admin | phase1 | ADM-5
/api/v1/causes | GET | cause, event | — | iOS, Android, Web | Guest | phase1 | DON-1
/api/v1/donations | POST | cause | donation, donation_allocation, payment_transaction, receipt, audit_log | iOS, Android, Web | Guest | phase1 | DON-2
/api/v1/donations/history | GET | donation, receipt, year_end_statement | — | iOS, Android, Web | Member | phase1 | DON-5
/api/v1/admin/causes | GET, POST, PATCH, DELETE | cause | cause, audit_log, tombstone | Admin | Committee Member | phase1 | DON-6
/api/v1/subscriptions | GET, POST | recurring_subscription | recurring_subscription, payment_method, audit_log | iOS, Android, Web | Member | phase1 | SUB-1
/api/v1/subscriptions/{id} | PATCH, DELETE | recurring_subscription | recurring_subscription, audit_log | iOS, Android, Web | Member | phase1 | SUB-2
/api/v1/admin/subscriptions/{id}/cancel | POST | recurring_subscription | recurring_subscription, audit_log | Admin | Admin (money permission, two-actor) | phase1 | SUB-5
/api/v1/families/{id} | GET, PATCH | family, family_member | family, family_member, audit_log | iOS, Android, Web | Family Primary | phase1 | MFD-1
/api/v1/families/{id}/dues | GET | dues_item, dues_ledger_entry | — | iOS, Android, Web | Family Primary | phase1 | MFD-2
/api/v1/families/{id}/dues/pay-all | POST | dues_item | payment_transaction, dues_ledger_entry, audit_log | iOS, Android, Web | Family Primary | phase1 | MFD-2
/api/v1/admin/families/merge | POST | family, family_member, donation, dues_ledger_entry | family, family_member, audit_log, tombstone | Admin | Admin | phase1 | MFD-4
/api/v1/admin/dues/credit | POST | dues_item | dues_ledger_entry, audit_log | Admin | Admin (money permission, two-actor) | phase1 | MFD-6
/api/v1/tithis/available | GET | tithi_slot | — | iOS, Android, Web | Guest | phase1 | SPN-1
/api/v1/sponsorships | POST | tithi_slot, pooja_slot, bhojanshala_slot | sponsorship, donation, audit_log | iOS, Android, Web | Guest | phase1 | SPN-1
/api/v1/religious-calendar/pooja | GET | pooja_slot, tradition | — | iOS, Android, Web | Guest | phase1 | SPN-2
/api/v1/admin/religious-calendar/pooja | POST, PATCH | pooja_slot | pooja_slot, audit_log | Admin | Committee Member | phase1 | SPN-5
/api/v1/community/posts | GET, POST | post, post_media, post_reaction, badge | post, post_media, audit_log | iOS, Android, Web | Guest (read), Member (post) | phase1 | COM-2
/api/v1/community/posts/{id}/report | POST | post | content_report | iOS, Android, Web | Member | phase1 | COM-3
/api/v1/admin/moderation/queue | GET | post, content_report | — | Admin | Committee Member | phase1 | COM-4
/api/v1/admin/moderation/{post_id}/decision | POST | post | post, moderation_action, audit_log | Admin | Committee Member | phase1 | COM-4
/api/v1/devices/register | POST | — | device_token | iOS, Android, Web | Guest | phase1 | NOT-2
/api/v1/notifications/preferences | GET, PATCH | notification_preference | notification_preference | iOS, Android, Web | Member | phase1 | NOT-2
/api/v1/admin/notifications/campaigns | GET, POST | notification_template, segment | notification_campaign, audit_log | Admin | Committee Member | phase1 | NOT-3
/api/v1/admin/segments | GET, POST | segment | segment | Admin | Committee Member | phase1 | NOT-4
/api/v1/admin/notifications/{id}/delivery-report | GET | delivery_receipt | — | Admin | Committee Member | phase1 | NOT-5
/api/v1/pathshala/my-children | GET | family_member, enrollment, pathshala_class, lesson | — | iOS, Android, Web | Pathshala Parent | phase1 | PS-1
/api/v1/admin/pathshala/enrollments | GET, POST, PATCH | enrollment, pathshala_class | enrollment, audit_log | Admin | Committee Member | phase1 | PS-3
/api/v1/volunteer/opportunities | GET | volunteer_opportunity | — | iOS, Android, Web | Guest | phase1 | VOL-1
/api/v1/volunteer/opportunities/{id}/signup | POST | volunteer_opportunity | volunteer_signup | iOS, Android, Web | Member | phase1 | VOL-1
/api/v1/admin/volunteer/hours | POST | — | volunteer_hour_log, audit_log | Admin | Committee Member | phase1 | VOL-3
/api/v1/live-darshan/streams | GET | tradition (stream config, not modeled as its own table in v1) | — | iOS, Android, Web | Guest | phase1 | LD-1
/api/v1/admin/live-darshan/streams/{tradition_id} | PATCH | tradition | integration_credential (stream URL ref), audit_log | Admin | Admin | phase1 | LD-4
/api/v1/admin/audit-log | GET | audit_log | — | Admin | Super-Admin | phase1 | GOV-1
/api/v1/admin/confirmations/{id}/confirm | POST | — (transient confirmation request, not a persisted table) | audit_log (both actors) | Admin | Admin (second actor) | phase1 | GOV-2
/api/v1/admin/trash/{table} | GET, POST (restore) | tombstone | tombstone, audit_log | Admin | Admin | phase1 | GOV-3
/api/v1/admin/feature-flags | GET, PATCH | feature_flag | feature_flag, audit_log | Admin | Super-Admin | phase1 | GOV-4
/api/v1/admin/credentials-vault | GET, POST | integration_credential | integration_credential, audit_log | Admin | Super-Admin | phase1 | GOV-6
/api/v1/public/pages/{slug} | GET | page | — | Web | Guest | phase1 | SEO-1
/api/v1/localization/catalog | GET | localization_string | — | iOS, Android, Web, Admin | Guest | phase0 | L10N-1
/api/v1/admin/localization/catalog | PATCH | localization_string | localization_string, audit_log | Admin | Committee Member | phase1 | L10N-5
/api/v1/account/delete | POST | user, donation | user (tombstoned/anonymized), donation (de-linked), audit_log | iOS, Android, Web | Member | phase1 | SEC-6
/api/v1/governance/minutes | GET | meeting_minute | — | iOS, Android, Web | Member (tier-gated) | phase2 | GOVD-1
/api/v1/admin/governance/minutes | POST, PATCH | meeting_minute | meeting_minute, audit_log | Admin | Committee Member | phase2 | GOVD-2
/api/v1/library/search | GET | media_asset (Meilisearch index of catalog content) | — | iOS, Android, Web | Guest | phase2 | LIB-1
/api/v1/pathshala-books/{grade} | GET | media_asset, enrollment | — | iOS, Android, Web | Pathshala Parent | phase2 | LIB-5
/api/v1/directory/businesses | GET, POST (submit listing) | — (business_listing table, extension of media_asset+content pattern) | — | iOS, Android, Web | Guest (read), Member (submit) | phase2 | DIR-1
/api/v1/facilities/{id}/book | POST | facility, facility_booking | facility_booking, payment_transaction, audit_log | iOS, Android, Web | Member | phase2 | DIR-3
/api/v1/admin/facility-bookings/{id}/decision | POST | facility_booking | facility_booking, audit_log | Admin | Committee Member | phase2 | DIR-4
/api/v1/service-awards/nominate | POST | — | service_award | iOS, Android, Web | Member | phase2 | REC-1
/api/v1/admin/reports/donor-cohort | GET | donation, member_profile | — | Admin | Admin (Treasurer) | phase2 | RPT-1
/api/v1/admin/localization/hi-gu/{key} | PATCH | localization_string | localization_string, audit_log | Admin | Committee Member | phase2 | L10N2-1
/api/v1/education/philosophy/tracks | GET | — (curriculum_track/lesson, Phase 3 addition to Education & Seva domain) | — | iOS, Android, Web | Member | phase3 | PHIL-1
/api/v1/chat/message | POST | — (knowledge-base index, separate AI Chat service) | — (conversation log in the AI Chat service's own store) | iOS, Android, Web | Member | phase3 | AI-C-3
/api/v1/admin/chat/escalations | GET | — (AI Chat service escalation store) | — | Admin | Committee Member | phase3 | AI-C-4

## Design Tokens & Palette
Token | Value | Role | Contrast vs Cream | AA Verdict | Surfaces
jca-ny-app_vSHARE.html is authoritative (RFP §2.2: "white marble, crimson, and gold — never saffron/orange"). jca-app-mockup.html and the entire jca-admin-mocukups.html file use an indigo/saffron palette and are treated as superseded design-exploration artifacts (Discovery item DISC-8). The admin utility's visual language is re-derived from these vSHARE tokens, not carried forward from its own mockup file.
--crimson | #a8202c | Primary brand color. Body text, primary buttons, active states, links. | 6.70:1 | Pass — AA normal text and AA large text | iOS, Android, Web, Admin
--crimson-deep | #7a1620 | Pressed/active states, headings on light backgrounds. | 9.93:1 | Pass — AAA normal text | iOS, Android, Web, Admin
--crimson-soft | #c84252 | Secondary accents, badges, non-critical highlights. | 4.47:1 | Pass — AA large text/UI only (fails AA normal text by 0.03; do not use for body copy) | iOS, Android, Web, Admin
--gold | #c9a961 | Ornamental only — borders, dividers, icon fills, decorative rules, ratnatraya/aṣṭamaṅgala motifs. | 2.09:1 | Fail — never use for text of any size | iOS, Android, Web, Admin
--gold-light | #e3c889 | Subtle background tints, hover fills behind icons — never text, never adjacent to cream as a foreground. | 1.51:1 | Fail — decorative background use only | iOS, Android, Web, Admin
--gold-deep | #8c6f30 | Legacy 'deep gold' token from vSHARE — retained only for large display headings (>=24px). | 4.40:1 | Fail — AA normal text (misses 4.5:1 threshold by 0.10); Pass — AA large text only | iOS, Android, Web, Admin
--gold-text (NEW — Discovery item DISC-10) | #7d6229 | AA-safe gold for any place gold-colored TEXT is genuinely needed (e.g. a gold pill label). Introduced because the vSHARE --gold and --gold-deep tokens both fail AA body text. | 5.34:1 | Pass — AA normal text | iOS, Android, Web, Admin
--cream | #faf6ef | Primary light background across all member-facing surfaces. | n/a (background reference) | n/a | iOS, Android, Web, Admin
--cream-warm | #f4ecdd | Secondary background — cards, elevated surfaces on cream. | n/a (background) | n/a | iOS, Android, Web, Admin
--paper | #ffffff | Elevated surfaces (modals, sheets) requiring maximum contrast. | n/a (background) | n/a | iOS, Android, Web, Admin
--ink | #1c1410 | Primary body text color. | 16.85:1 | Pass — AAA normal text | iOS, Android, Web, Admin
--ink-soft | #4a3d35 | Secondary text — captions, metadata, timestamps. | 9.70:1 | Pass — AAA normal text | iOS, Android, Web, Admin
--muted | #8a7864 | Tertiary text and disabled states — placeholder text, inactive tab labels. | 3.94:1 | Pass — AA large text/UI only (fails AA normal text; do not use for body copy or form labels) | iOS, Android, Web, Admin
--good | #3f7d5e | Success states — confirmed payment, approved content, open/available status. | n/a (compute per use; verify before shipping any new success-state text) | Verify per use | iOS, Android, Web, Admin
Typography
Display / serif headings | Fraunces (serif) | Screen titles, ornamental headings, the JCA wordmark treatment.
Body / UI text | Inter (sans-serif), -apple-system fallback | All body copy, form labels, buttons, navigation labels.
Dynamic Type / accessibility | Both families scale with iOS Dynamic Type and Android font scaling; no hard-coded pixel line-heights — RFP §2.2 multi-generational accessibility requirement. | Applies platform-wide; verified per screen in the accessibility audit (Localization & Accessibility module).
Spacing & Shape
Border radius (member surfaces) | Card: 16-20px · Button/chip: full-pill · Modal sheet: 24px top corners
Border radius (admin utility, from indigo mockup's --r tokens, re-themed) | --r: 12px · --r-sm: 8px · --r-lg: 18px (denser than member surfaces, matches admin's productivity-first brief)
Shadow — small | 0 1px 2px rgba(28,20,16,0.04), 0 1px 3px rgba(28,20,16,0.06)
Shadow — medium | 0 4px 12px rgba(28,20,16,0.08), 0 2px 4px rgba(28,20,16,0.04)
Iconography: Jain symbology only: siddhachakra, swastika (Jain form), aṣṭamaṅgala, ratnatraya (three-jewel ornament), the five-shrine iconset (Mahavir, Adinath, Upashray, Shrimad, Dadawadi). Explicitly excluded: Om, Ganesha, trishul, or any Hindu iconography — RFP §2.2 "Jain, not Hindu."
Dark mode: Live Darshan and Virtual Tour ship dedicated dark-mode UI per the walkthrough deck (slides 4 and 6). Dark-mode tokens are derived from the same crimson/gold/ink palette, not a separate theme, so brand identity holds in both modes.

## UI-UX Design - Mobile
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DES-M-1 | As the design lead, I want to extract and formalize the design-token set from jca-ny-app_vSHARE.html so every surface builds against one authoritative palette. | Token file published (colors, type, spacing, radii, shadows) matching vSHARE; jca-app-mockup.html and jca-admin-mocukups.html palettes formally marked superseded; sign-off recorded from JCA project committee per RFP §2.3. | - Diff vSHARE vs jca-app-mockup vs admin-mockup token sets - Write the palette-conflict resolution memo (Discovery item DISC-8) - Publish packages/tokens source file (JSON/YAML) consumed by web, admin, and RN | iOS, Android, Web, Admin | Critical | Medium | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-2 | As the design lead, I want the gold token family remediated for WCAG 2.1 AA so no on-brand color choice silently fails accessibility. | New --gold-text token (#7d6229, 5.34:1 vs cream) introduced; gold and gold-light restricted to ornamental/non-text use in the component library; contrast table (Discovery item DISC-10) reviewed and signed off. | - Compute contrast ratios for every token against cream and paper backgrounds - Introduce --gold-text and document the 'gold is ornament, crimson is text' rule - Update Figma color styles and component variants to enforce the rule | iOS, Android, Web, Admin | Critical | Low | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-3 | As a designer, I want all 28 mobile screens redrawn in Figma against the corrected tokens so engineering has a pixel-accurate, accessible source of truth. | All 28 screens from the walkthrough deck present in Figma with corrected tokens applied; each screen annotated with the navigation paths from the walkthrough; JCA committee review completed. | - Recreate all 28 screens (Home, Live Darshan, Calendar, Donate flows, Community, Profile/More, etc.) - Annotate navigation paths per the walkthrough deck's 'How to Navigate' sections - Run a design-review session with the JCA project committee | iOS, Android | Critical | High | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-4 | As a designer, I want dark-mode variants for Live Darshan and Virtual Tour so the meditative viewing context is honored as specified. | Dark-mode screens for Live Darshan (5 shrine streams) and Virtual Tour designed using the same brand tokens; contrast verified in dark mode. | - Design dark-mode Live Darshan screen with PiP and stream selector - Design dark-mode Virtual Tour with 360° hotspot overlay - Verify AA contrast for all dark-mode text/icon combinations | iOS, Android | High | Medium | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-5 | As a designer, I want Dynamic Type and platform font-scaling verified across representative screens so multi-generational accessibility (ages 5-90+) is honored. | Home, Donate, and Family/Dues screens verified at 100%, 150%, and 200% text scale on iOS and Android without truncation or overlap; tap targets meet platform minimums at every scale. | - Test Dynamic Type scaling on iOS reference screens - Test font-scale accessibility settings on Android reference screens - Document minimum tap-target sizes in the component spec | iOS, Android | High | Medium | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-6 | As a designer, I want a Jain iconography set (siddhachakra, aṣṭamaṅgala, ratnatraya, swastika) so the visual identity is unambiguously Jain, not Hindu. | Icon set delivered as SVG/vector assets for all five icon families; no Om, Ganesha, or trishul iconography present anywhere in the set; JCA committee confirms religious accuracy. | - Source/commission the five core Jain icon families - Build the five-shrine iconset (Mahavir, Adinath, Upashray, Shrimad, Dadawadi) - Get religious-accuracy sign-off from JCA committee | iOS, Android, Web, Admin | Critical | Medium | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
DES-M-7 | As a designer, I want a motion spec so transitions feel calm and reverent rather than growth-hacky, per the 'calm over flashy' principle. | Motion spec documents easing curves, durations, and prohibited patterns (no confetti/gamified animation on member surfaces); applied to the Thank You (donation confirmation) screen as the reference implementation. | - Define easing/duration tokens (calm, deliberate transitions) - Document prohibited patterns per the 'calm over flashy' RFP principle - Prototype the Anumodana Thank You screen animation as the reference case | iOS, Android, Web | Medium | Low | Phase 0 — Foundation | S1-S2 (Weeks 1-4) | Ready
Sprint: S1-S2 · Weeks 1-4 · Sprint Complexity: Very High · Gate: Design review — 28 mobile screens signed off with the corrected, AA-compliant palette

## UI-UX Design - Web and Admin
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DES-W-1 | As a designer, I want a responsive web design system derived from the mobile tokens so brand identity is consistent while layouts adapt to viewport. | Breakpoints defined (mobile/tablet/desktop); responsive grid derived from the 5-tab structure as a top navigation bar per RFP §3.3; component library published in Figma with web-specific states (hover, focus-visible). | - Define breakpoints and responsive grid system - Design the top-nav bar mirroring the 5 mobile tabs plus public-info area - Publish web component library (buttons, cards, forms, tables) | Web | Critical | High | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
DES-W-2 | As a designer, I want a clearly differentiated public-vs-member navigation on web so unauthenticated visitors and signed-in members each see the right experience. | Public homepage designed for unauthenticated visitors (info, event browse, donate, newsletter); authenticated member navigation mirrors the 5-tab mobile IA; sign-in CTA placement consistent across public pages. | - Design public homepage and public information pages - Design authenticated member web dashboard mirroring mobile Home - Design the sign-in/sign-up entry points across public pages | Web | Critical | Medium | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
DES-W-3 | As a designer, I want an admin visual language re-derived from the vSHARE tokens (not the superseded indigo/saffron admin mockup) so the admin utility stays on-brand while remaining dense and productivity-first. | Admin theme uses crimson/gold/cream/ink tokens instead of the indigo/saffron mockup; sidebar, nav-groups, and status badges (good/warn/danger) redefined against the new palette; density and layout patterns from the original admin mockup retained where they don't conflict with brand. | - Re-theme the admin mockup's sidebar, nav, and status colors to vSHARE tokens - Verify AA contrast on all re-themed admin components - Document the density/spacing scale (--r, --r-sm, --r-lg) carried forward from the original admin mockup | Admin | Critical | High | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
DES-W-4 | As a designer, I want the admin ⌘K command palette and bulk-action patterns specified so common admin operations are keyboard-first, per RFP §4.4.1. | Command palette UI spec covers search-everywhere, quick navigation, and quick actions; bulk-action pattern (checkbox select-all, bulk toolbar) specified for at least one reference list (Members). | - Design the ⌘K command palette overlay and result list - Design the bulk-action toolbar pattern for list views - Specify keyboard shortcuts for the five most common admin operations | Admin | High | Medium | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
DES-W-5 | As a designer, I want a data-table component spec covering saved filters, sorting, and pagination so every admin list view is built consistently. | Data-table spec covers column sort, saved-filter chips, pagination, empty states, and loading states; applied as the reference for the Members & Families list. | - Design the base data-table component with sort/filter/paginate states - Design saved-filter chip pattern - Apply the pattern to the Members & Families list as the reference build | Admin | High | Medium | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
DES-W-6 | As a designer, I want a component inventory audit so I know exactly which components are shared across web, admin, and mobile via packages/tokens versus surface-specific. | Component inventory spreadsheet lists every component with a Shared/Surface-specific tag; shared components mapped to their packages/ui implementation target. | - Audit all components across the three Figma files - Tag each as Shared or Surface-specific - Hand off the shared list to engineering for packages/ui scaffolding | Web, Admin, iOS, Android | Medium | Low | Phase 0 — Foundation | S2-S3 (Weeks 3-6) | Ready
Sprint: S2-S3 · Weeks 3-6 · Sprint Complexity: High · Gate: Design review — responsive web navigation + admin component inventory

## Architecture and Tech Stack
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
ARCH-1 | As the tech lead, I want the stack ratified and recorded as ADRs so every subsequent decision traces back to a documented rationale. | ADRs written for web framework, admin frontend, mobile framework, backend framework, database, payments, search, hosting, streaming, and monorepo tooling — matching the Tech Decisions sheet; each ADR includes the offense/defence and a named owner. | - Write one ADR per decision row in the Tech Decisions sheet - Circulate ADRs to the JCA technical advisor for review per RFP §4.1.1 - File signed-off ADRs in the repository under /docs/adr | Backend, Web, Admin, iOS, Android | Critical | Medium | Phase 0 — Foundation | S1 (Weeks 1-2) | Ready
ARCH-2 | As a mobile engineer, I want a spike proving Picture-in-Picture, AirPlay, and Google Cast work in an Expo dev-client build before Live Darshan is scheduled as a feature sprint. | A throwaway Expo dev-client build demonstrates PiP on iOS, AirPlay casting to an Apple TV, and Google Cast to a Chromecast, all playing a test HLS stream; findings documented, blocking risks flagged. | - Configure react-native-video v6 with a custom dev client - Configure react-native-google-cast and verify Cast discovery - Document build-config gotchas for the eventual Live Darshan sprint | iOS, Android | Critical | High | Phase 0 — Foundation | S1 (Weeks 1-2) | Ready
ARCH-3 | As the tech lead, I want the monorepo topology (Turborepo + pnpm) scaffolded so every surface shares tokens and the generated API client from day one. | Monorepo created with apps/web, apps/admin, apps/mobile, packages/tokens, packages/api-client, packages/validation, and services/api; a shared token change in packages/tokens visibly propagates to a placeholder page in each app. | - Scaffold the pnpm workspace and Turborepo pipeline config - Create empty apps/* and packages/* with a shared tsconfig base - Prove token propagation with a trivial color-swap test | Backend, Web, Admin, iOS, Android | Critical | Medium | Phase 0 — Foundation | S1 (Weeks 1-2) | Ready
ARCH-4 | As the tech lead, I want environment topology (local, staging, production) defined so every surface and the backend deploy predictably. | Environment matrix documents URLs, config sources, and data-isolation rules for local/staging/production across all five deliverables; admin utility staging vs production promotion flow documented per RFP §4.4.2. | - Define environment variable and secrets strategy per environment - Document the staging-to-production promotion flow for content - Provision the three GCP projects/environments | Backend, Web, Admin | High | Medium | Phase 0 — Foundation | S1 (Weeks 1-2) | Ready
Sprint: S1 · Weeks 1-2 · Sprint Complexity: High · Gate: Internal — architecture decision records approved

## Database Schema and Data Model
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DB-1 | As a backend engineer, I want the nine-domain data model designed and reviewed so every subsequent feature sprint builds against a stable schema. | ERD covers all nine domains (Identity & Access, Membership, Giving, Sponsorship, Events & Facilities, Community, Content, Education & Seva, Platform Operations) per docs/03-database-schema.md; reviewed by JCA's technical advisor per RFP §4.1.1. | - Draft the ERD for each of the nine domains - Cross-check every table against RFP §3.4 and §4.5 component requirements - Circulate for technical-advisor review and incorporate feedback | Backend | Critical | Very High | Phase 0 — Foundation | S2 (Weeks 3-4) | Ready
DB-2 | As a backend engineer, I want the cross-cutting conventions (UUID PKs, soft-delete tombstone, optimistic-locking version column, audit trigger) applied to every table via a shared Django abstract base model. | An abstract BaseModel provides id, created_at, updated_at, created_by, updated_by, deleted_at, and version; django-safedelete and django-simple-history wired at the base-model level so every concrete model inherits soft-delete and audit history for free. | - Implement the shared abstract base model - Wire django-safedelete for the 30-day tombstone/recovery workflow - Wire django-simple-history for the immutable audit trail | Backend | Critical | High | Phase 0 — Foundation | S2 (Weeks 3-4) | Ready
DB-3 | As a backend engineer, I want the existing database JCA referenced in the RFP audited so we know what, if anything, must be migrated before the new schema is frozen. | Discovery item DISC-9 resolved: audit report documents the existing system(s), including the library-book database from RFP §3.4 item 15, its schema, row counts, and export capability; migration-path recommendation delivered. | - Request database access/export from JCA IT contact - Profile the existing library-book catalog structure and volume - Write the migration-path recommendation as part of DISC-9 | Backend | Critical | Medium | Phase 0 — Foundation | S2 (Weeks 3-4) | Ready
DB-4 | As a backend engineer, I want baseline Django migrations and seed data so every developer can stand up an identical local database. | Initial migration set applies cleanly on a fresh Postgres 16 instance; seed-data fixture populates roles, permissions, the five traditions, and a handful of demo members/events for local development. | - Generate and review the initial migration set - Write the roles/permissions/traditions seed fixture - Document the local-dev database bootstrap command | Backend | High | Medium | Phase 0 — Foundation | S2 (Weeks 3-4) | Ready
DB-5 | As a backend engineer, I want pg_trgm and unaccent enabled with indexes on searchable name/content fields so search is typo-tolerant and diacritic-aware from day one. | pg_trgm and unaccent extensions enabled on the Postgres instance; trigram indexes added on member_profile.display_name, event.title, and post.body; a manual test query with a typo and a missing diacritic both return the expected row. | - Enable pg_trgm and unaccent extensions via migration - Add trigram GIN indexes on the identified searchable columns - Write a smoke test proving typo-tolerant, diacritic-insensitive matches | Backend | High | Low | Phase 0 — Foundation | S2 (Weeks 3-4) | Ready
Sprint: S2 · Weeks 3-4 · Sprint Complexity: High · Gate: Schema review — ERD approved, legacy-DB audit complete

## API Contract and Integration Ma
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
API-1 | As a backend engineer, I want drf-spectacular wired into the Django project so an OpenAPI 3.1 schema is generated automatically from the DRF viewsets and serializers. | OpenAPI schema auto-generates at /api/schema/; a Swagger/Redoc UI is reachable in the staging environment; schema includes example payloads for at least the auth and member-profile endpoints. | - Install and configure drf-spectacular - Annotate initial viewsets with example payloads - Publish the schema UI to staging | Backend | Critical | Medium | Phase 0 — Foundation | S3 (Weeks 5-6) | Ready
API-2 | As a frontend engineer, I want a TypeScript API client generated from the OpenAPI schema into packages/api-client so web, admin, and mobile call the backend through one typed interface. | A codegen script produces a typed client from the live schema; a change to a backend serializer field is reflected in the generated client on the next codegen run without manual edits; client published as a workspace package consumed by all three frontend apps. | - Select and configure the OpenAPI-to-TypeScript codegen tool - Wire codegen into the CI pipeline as a drift-check - Consume the generated client from a placeholder screen in each app | Web, Admin, iOS, Android | Critical | Medium | Phase 0 — Foundation | S3 (Weeks 5-6) | Ready
API-3 | As a backend engineer, I want an API versioning and deprecation policy documented so breaking changes never surprise a shipped mobile client, per RFP §3.1. | Versioning policy documented (URL-prefixed /api/v1/); deprecation window defined (minimum 90 days with a Sunset header); policy referenced in every ADR touching the API surface. | - Document the versioning scheme and deprecation window - Implement a Sunset-header middleware for deprecated routes - Add the policy to the onboarding docs for new engineers | Backend | High | Low | Phase 0 — Foundation | S3 (Weeks 5-6) | Ready
API-4 | As a backend engineer, I want a standard error envelope and pagination/filtering convention so every endpoint behaves predictably across all four surfaces. | Error responses follow a consistent {code, message, field_errors} shape; list endpoints support cursor-based pagination and a common filter/sort query-param convention; documented in the API contract. | - Implement a shared DRF exception handler for the error envelope - Implement a shared pagination class - Document the filtering/sorting query-param convention | Backend | High | Medium | Phase 0 — Foundation | S3 (Weeks 5-6) | Ready
Sprint: S3 · Weeks 5-6 · Sprint Complexity: High · Gate: Phase 0 exit gate — OpenAPI contract published and approved (RFP §4.1.1, §6.1.1 item 1)

## Project Setup and CI-CD
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
SETUP-1 | As a DevOps engineer, I want five project skeletons (backend, web, admin, mobile, infra) created with CI so every surface builds and lints on every push, per RFP §4.1.1. | Each skeleton has a passing CI pipeline running build + lint + test on every push; badge visible in each app's README; a trivial change to each surface triggers and passes its pipeline. | - Scaffold the Django backend skeleton with pytest + ruff - Scaffold the Next.js web skeleton with ESLint + Prettier + TypeScript strict - Scaffold the Vite admin skeleton with the same linting stack - Scaffold the Expo mobile skeleton with ESLint + TypeScript strict | Backend, Web, Admin, iOS, Android | Critical | High | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
SETUP-2 | As a DevOps engineer, I want reproducible, signed, tagged releases so every deployed artifact traces back to an exact commit. | A tagged release produces an identical Docker image digest on a repeat build; releases are cryptographically signed; a release-notes template is used for every tag. | - Pin dependency lockfiles across all five projects - Configure reproducible Docker builds for the backend - Set up release signing and the release-notes template | Backend, Web, Admin | High | Medium | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
SETUP-3 | As a DevOps engineer, I want EAS Build profiles configured for the monorepo so iOS and Android builds come from one pipeline without dual-build overhead. | eas.json defines development, preview, and production profiles; a build triggered from CI produces both an iOS simulator build and an Android APK from the same commit. | - Configure eas.json profiles for dev/preview/production - Wire EAS Build into the monorepo's CI trigger - Verify a dual iOS+Android build from a single commit | iOS, Android | Critical | Medium | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
SETUP-4 | As a DevOps engineer, I want infrastructure as code for the GCP environment so staging and production are provisioned identically and repeatably. | Terraform (or equivalent) provisions Cloud Run services, Cloud SQL instance, Cloud Storage buckets, and Secret Manager entries for both staging and production from the same module with environment-specific variables. | - Write Terraform modules for Cloud Run, Cloud SQL, and Cloud Storage - Parameterize staging vs production variables - Provision both environments and verify parity | Backend | Critical | High | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
SETUP-5 | As a DevOps engineer, I want Cloud Build (or equivalent) wired to deploy on merge to main so every accepted change reaches staging without a manual step. | A merge to main triggers build, test, and deploy to staging for the affected surface(s) only; a failed pipeline blocks the deploy and notifies the team. | - Configure Cloud Build triggers per surface - Wire failure notifications to the team channel - Verify path-based triggers only rebuild affected surfaces | Backend, Web, Admin | High | Medium | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
Sprint: S1-S3 · Weeks 1-6 · Sprint Complexity: High · Gate: Internal — five green CI pipelines, staging deploys live

## Auth Identity and RBAC
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
AUTH-1 | As a member, I want to sign in with Apple, Google, or email/password on any surface so I have one identity everywhere, per RFP §3.1. | All three sign-in methods work on iOS, Android, and Web; signing in on one surface and then opening another surface recognizes the same account; django-allauth backs all three providers server-side. | - Wire django-allauth for Apple and Google OAuth - Implement email/password registration with verification - Build the sign-in UI on all three member surfaces | iOS, Android, Web, Backend | Critical | High | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-2 | As a new member, I want registration to capture member-ID linkage, family-record initiation, and gotra so my account starts connected to my family and tradition. | Registration flow collects member ID (or issues one), initiates a family record with the registrant as primary, and captures gotra and tradition; all three fields visible on the resulting Profile screen. | - Design and build the registration form with member-ID/family/gotra fields - Implement member-ID issuance logic for brand-new registrants - Auto-create the family record on registration completion | iOS, Android, Web, Backend | Critical | Medium | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-3 | As an admin, I want an SSO option for admin sign-in so JCA can use its provider of choice for staff authentication, per RFP §3.1. | SAML or OIDC SSO configurable in Settings > Integration Credentials; an admin can sign in via the configured SSO provider in addition to email/password. | - Integrate a generic SAML/OIDC SSO connector in the admin app - Build the SSO configuration UI in admin Settings - Test against at least one real SSO provider (e.g. Google Workspace SSO) | Admin, Backend | High | Medium | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-4 | As an admin, I want MFA mandatory at first login so the admin utility meets the security posture confirmed in Discovery (item DISC-4). | An admin cannot complete first login without enrolling an MFA factor (TOTP at minimum); MFA is enforced on every subsequent login; no bypass path exists for any admin role including Super-Admin. | - Implement TOTP-based MFA enrollment and verification - Enforce MFA at first login with no skip option - Add MFA re-verification for the two-person money-confirmation flow | Admin, Backend | Critical | Medium | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-5 | As a member, I want the option to enable MFA on my account so I can add security if I choose, without it being forced. | MFA enrollment is available in Profile > Settings for member accounts; enabling it does not disrupt Sign in with Apple/Google flows; disabling requires re-authentication. | - Expose optional MFA enrollment in member Settings - Handle MFA verification within the Apple/Google sign-in flow - Require re-auth before MFA can be disabled | iOS, Android, Web, Backend | Medium | Low | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-6 | As a Super-Admin, I want to define roles and per-section permission overrides so access matches RFP §3.1's minimum seven-role set plus any additional roles we need. | Role and permission editor lets a Super-Admin create/edit roles and assign per-section read/write/approve/money permissions; a 'what can this role see and do' preview is available; the Treasurer/Pathshala-coordinator/Communications-chair scenarios from RFP §4.4.1 are each configurable without code changes. | - Build the role and permission editor UI - Implement the permission-preview feature - Seed the seven baseline roles (Guest, Member, Family Primary, Pathshala Parent, Committee Member, Admin, Super-Admin) | Admin, Backend | Critical | High | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-7 | As a mobile/web engineer, I want tokens stored in the platform keychain/keystore/HttpOnly cookie so credentials never sit in insecure storage, per RFP §5.1. | iOS stores tokens in Keychain with the strictest applicable accessibility class; Android uses Keystore-backed EncryptedSharedPreferences; web sessions use HttpOnly, Secure, SameSite=Lax cookies with CSRF tokens on state-changing requests. | - Implement Keychain-backed token storage on iOS - Implement Keystore-backed token storage on Android - Implement HttpOnly/Secure/SameSite cookie sessions with CSRF protection on web | iOS, Android, Web, Backend | Critical | Medium | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
AUTH-8 | As a first-time mobile user, I want a first-launch Splash/Welcome screen establishing Jain identity before any utility, so my first impression of the app is reverent, not transactional, per RFP §4.1.2 and the walkthrough's slide 4. | Splash shows the JCA logo on an ivory medallion, the Navkar Mantra in a serif face, the ratnatraya ornament, and the five-shrine context (Mahavir, Adinath, Upashray, Shrimad, Dadawadi), with a single Get Started CTA; shown automatically on first open and never again unless the user signs out; web equivalent is the public homepage with a Sign In CTA (no separate splash screen on web). | - Build the mobile Splash/Welcome screen with the Jain iconography from DES-M-6 - Implement the first-open-only display logic, reset on sign-out - Verify the web public homepage serves as the equivalent entry point | iOS, Android, Web | Critical | Low | Phase 0 — Foundation | S3-S4 (Weeks 5-8) | Ready
Sprint: S3-S4 · Weeks 5-8 · Sprint Complexity: High · Gate: Sprint demo — sign-in working end-to-end on all three member surfaces

## Discovery and Open Items
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DISC-S-1 | As the JCA project committee, we want every RFP §4.6 discovery item resolved with a written recommendation before feature work begins, so scope is unambiguous. | All ten rows on the Discovery & Open Items control sheet carry a resolution, an owner, and a resolve-by sprint; unresolved items block the Phase 0 exit gate. | - Run Discovery workshops with the JCA project committee per RFP §4.1.1 - Walk through each of the ten Discovery items and capture a decision - Circulate the finalized Discovery report as a Phase 1 deliverable input (RFP §6.1.1 item 1) | Backend, Web, Admin, iOS, Android | Critical | Medium | Phase 0 — Foundation | S1-S3 (Weeks 1-6) | Ready
Sprint: S1-S3 · Weeks 1-6 · Sprint Complexity: Medium · Gate: Phase 0 exit gate — every §4.6 item resolved and signed off, per RFP §6.1.1

## Home and Panchang
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
HP-1 | As a member, I want an eight-section Home dashboard so I have a single daily-touch landing page with everything I check each morning. | Home renders greeting, Panchang card, Today's Sponsor, Thought of the Day, Daily Quiz, Quick Actions, Center Hours, and Upcoming Events + Feed preview, matching the walkthrough's slide 3; pull-to-refresh updates Panchang and feed. | - Build the eight-section responsive grid layout - Wire each section to its backend endpoint - Implement pull-to-refresh on mobile | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
HP-2 | As a member, I want the daily Jain Panchang (tithi, parva indicator, sunrise, sunset, pratikraman time) cached locally so I can check it even without a connection. | Panchang card shows all five data points; mobile caches the last-fetched Panchang for offline display; web shows the same data without requiring sign-in per RFP §4.1.2. | - Build the Panchang data endpoint with a configurable data source - Implement local offline cache on iOS/Android - Expose Panchang publicly (unauthenticated) on web | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
HP-3 | As an admin, I want to configure the Panchang data source and set manual overrides so incorrect calculated data can be corrected without a deploy. | Admin Religious Calendar section exposes a Panchang data-source configuration and a manual-override field per date; overrides take effect immediately on all surfaces. | - Build the Panchang data-source config UI - Implement per-date manual override with immediate propagation - Add pratikraman-time scheduling controls | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
HP-4 | As a member, I want a Daily Quiz with a streak counter so I have a reason to open the app every day. | One quiz question served per day; answering correctly/incorrectly is recorded once per user per day; a visible streak counter increments on consecutive correct days and resets on a missed day. | - Build the quiz-question serving and answer-recording endpoint - Implement the streak-calculation logic - Build the quiz UI with streak display on mobile and web | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
HP-5 | As an admin, I want to author Thought of the Day content and manage the quiz question bank so Home stays fresh without engineering involvement. | Content section lets an admin schedule a Thought of the Day per date and add/edit/retire quiz questions with a correct-answer flag; scheduled publish works for both content types. | - Build the Thought of the Day authoring UI with scheduling - Build the quiz question bank CRUD UI - Wire both to scheduled publish | Admin, Backend | High | Low | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
HP-6 | As a member, I want Quick Actions and Center Hours with an Open-Now indicator so I can act on the most common tasks and know if the center is open right now. | Quick Actions link to Darshan, Donate, Calendar, Gallery, and Volunteer; Center Hours shows today's hours with a live Open/Closed indicator based on the current time. | - Build the Quick Actions tile row with deep links - Build the Center Hours card with live open/closed calculation - Wire Center Hours to an admin-editable schedule | iOS, Android, Web, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S4 (Weeks 7-8) | Ready
Sprint: S4 · Weeks 7-8 · Sprint Complexity: Medium · Gate: Sprint demo

## Calendar and Events
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
CAL-1 | As a member, I want a month-grid calendar with festivals, parva days, and JCA events marked so I can see everything happening at a glance. | Month grid shows saffron-replaced (brand-compliant) markers for festival/parva days and separate markers for JCA event days per the walkthrough's slide 8; today is highlighted; tapping a day shows that date's events; swipe changes month. | - Build the month-grid calendar component - Wire festival/parva day markers from the religious calendar data - Implement day-tap and swipe-to-change-month interactions | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CAL-2 | As a member, I want an event detail view with full schedule, location, RSVP, and calendar export so I can commit to attending and add it to my phone. | Event detail shows hero image, full multi-block schedule, shrine/location with map preview, RSVP button with live attendee count, sponsor-this-event link, and an add-to-calendar action per the walkthrough's slide 22. | - Build the event detail screen layout - Implement RSVP with live attendee count - Implement calendar export (.ics) on mobile and web | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CAL-3 | As a member, I want to RSVP to an event and see a waitlist state if it's full so I know where I stand. | RSVP button shows Confirmed/Waitlisted/Full based on the RSVP cap; a waitlisted member is promoted automatically if a confirmed spot opens; cancellation frees the spot immediately. | - Implement RSVP cap and waitlist logic - Implement auto-promotion on cancellation - Build the RSVP status UI states | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CAL-4 | As an admin, I want full event lifecycle management (create, edit, publish, retire) with categories, RSVP cap, and sponsorship tiers so I run every event through one tool. | Event editor supports hero media, multi-block schedule, location, category (Religious/Cultural/Educational), RSVP cap, waitlist, sponsorship tiers, and linking a donation cause; publish/retire states are explicit and reversible within the soft-delete window. | - Build the Event editor with all specified fields - Implement publish/retire state transitions - Wire the cause-linking control for event-based donation prioritization | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CAL-5 | As an admin, I want a calendar conflict view across events, pooja, abhishek, and facility bookings so double-bookings are caught before publish. | Conflict view overlays events, religious-calendar slots, and facility bookings on one calendar; a scheduling conflict is visually flagged before an admin can publish the conflicting item. | - Build the cross-section conflict-view calendar component - Implement conflict-detection logic across the four source types - Block publish (with an override option) when a conflict is detected | Admin, Backend | High | High | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CAL-6 | As an admin, I want event category management (Religious/Cultural/Educational) so Cultural & Religious events surface correctly as filterable categories per RFP §4.1.2. | Category CRUD available in admin; member-facing Calendar supports filtering by category; Cultural events (Garba, plays, music programs) correctly tag as Cultural. | - Build category CRUD in admin - Add category filter chips to the member-facing Calendar - Backfill category taxonomy from the RFP's event examples | Admin, iOS, Android, Web | Medium | Low | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
Sprint: S5 · Weeks 9-10 · Sprint Complexity: Medium · Gate: Sprint demo

## Content and Newsletter
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
CN-1 | As an admin, I want to author and schedule announcements that push to all members and pin in the feed so time-sensitive news reaches everyone. | Announcement editor supports send-now or schedule-for-later; on publish, a push notification fans out and the announcement auto-pins in the Community Feed; preview renders as it will appear on iOS, Android, and web before publish, per RFP §4.4.1. | - Build the announcement composer with scheduling - Wire publish to push-notification fan-out and feed pinning - Build the multi-surface preview | Admin, iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CN-2 | As a visitor or member, I want About Us, Contact, and Help pages so I can learn JCA's history and get in touch. | About Us shows JCA history content; Contact shows address, phone, email, directions, hours, and social links; Help combines FAQ with a contact form that routes submissions to admin. | - Build the About Us, Contact, and Help pages - Wire the contact form to route submissions into the admin utility - Make all three pages publicly accessible without sign-in | iOS, Android, Web, Backend | Critical | Low | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CN-3 | As an admin, I want to manage the FAQ taxonomy and route contact-form submissions so Help content stays organized and no inquiry is lost. | FAQ entries are categorized and orderable; contact-form submissions appear in an admin queue with status tracking (new/responded/closed). | - Build the FAQ taxonomy management UI - Build the contact-form submission queue - Add status tracking and internal notes to submissions | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CN-4 | As a member, I want a public Board of Trustees and Executive Committee directory so I know who governs JCA. | Directory shows name, role, term, opt-in photo, and bio for each member; photo display respects each individual's opt-in flag. | - Build the public roster directory page - Implement per-member photo opt-in capture in admin - Wire term tracking so past terms are distinguishable from current | iOS, Android, Web, Backend | High | Low | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CN-5 | As a member, I want a newsletter archive with the current issue and back issues so I can catch up on anything I missed. | Current issue displayed prominently; archive lists back issues chronologically; share and save actions work on mobile and web. | - Build the newsletter archive list and issue-detail view - Implement share/save actions - Wire the admin newsletter composer to publish into this archive | iOS, Android, Web, Backend | Medium | Medium | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
CN-6 | As a non-member visitor, I want to subscribe to JCA's mailing list from the public web so I can stay informed without creating a full account. | Public opt-in form captures email with double opt-in confirmation; subscription integrates with JCA's existing email-marketing tool; admin can view and export the subscriber list. | - Build the public subscribe form with double opt-in - Integrate with JCA's existing email-marketing tool via API - Build the admin subscriber-list view with export | Web, Admin, Backend | Medium | Medium | Phase 1 — v1.0 (initial launch) | S5 (Weeks 9-10) | Ready
Sprint: S5 · Weeks 9-10 · Sprint Complexity: Medium · Gate: Sprint demo

## Payments and Billing
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
PAY-1 | As a backend engineer, I want Stripe integrated with Apple Pay, Google Pay, card, and ACH so every donation/dues/sponsorship flow has a working payment rail. | Stripe Payment Element live on web; Stripe React Native SDK live on iOS/Android with native Apple Pay and Google Pay sheets; a test charge completes end-to-end and a payment_transaction row is written. | - Integrate Stripe Payment Element on web - Integrate Stripe RN SDK with Apple Pay and Google Pay on mobile - Wire webhook handling for payment confirmation | iOS, Android, Web, Backend | Critical | Very High | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
PAY-2 | As a backend engineer, I want PayPal Commerce Platform integrated as a second payment rail so the RFP's explicit PayPal requirement is satisfied alongside Stripe. | PayPal button/flow available on all donation, dues, and sponsorship checkout screens as an alternative to Stripe; a completed PayPal payment writes the same payment_transaction shape as a Stripe payment. | - Integrate PayPal Commerce Platform SDK on web and mobile - Normalize PayPal webhook events into the shared payment_transaction model - Add PayPal as a selectable option on the Payment screen | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
PAY-3 | As a member, I want an explicit confirmation screen with itemized lines before any charge so I always know exactly what I'm paying for, per RFP §2.2. | Every payment flow (donation, dues, sponsorship, subscription, facility deposit) routes through a shared confirmation screen with itemized amount, cause/purpose, and payment method before the charge fires; no charge occurs without this screen. | - Build the shared payment-confirmation screen component - Wire every payment-initiating flow through this shared component - Add the Anumodana confirmation language above the Pay button | iOS, Android, Web | Critical | Medium | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
PAY-4 | As a backend engineer, I want every payment operation to be idempotent so a network retry or double-tap never double-charges a member. | Every charge request carries a client-generated idempotency key; a repeated request with the same key returns the original result without creating a second transaction; verified with an automated retry test. | - Implement idempotency-key generation on the client - Enforce idempotency-key uniqueness on the backend charge endpoint - Write an automated test simulating a duplicate request | Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
PAY-5 | As a member, I want a downloadable PDF tax receipt for every donation and a consolidated year-end statement so my 501(c)(3) giving is documented, per RFP §2.2. | Every completed donation generates a PDF receipt with JCA's EIN and 'no goods or services' language within seconds of payment; a year-end statement PDF aggregates all giving for a tax year and is downloadable on demand. | - Build the PDF receipt generation service - Build the year-end statement aggregation and PDF generation - Wire receipt/statement download buttons across Donation History and Thank You screens | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
PAY-6 | As an admin, I want to record off-platform donations (cash, check, in-kind) and issue refunds, both gated by the two-person rule, so financial operations stay auditable. | Manual donation-entry form generates a receipt identically to an on-platform donation; a refund action requires a second admin's confirmation with their own credentials before it commits; both actions write audit-log entries naming both actors. | - Build the manual donation-entry component - Build the refund flow with the two-person confirmation modal - Verify audit-log entries capture both actors for both operations | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S6 (Weeks 11-12) | Ready
Sprint: S6 · Weeks 11-12 · Sprint Complexity: Very High · Gate: Sprint demo — first real charge processed in staging

## Admin Shell Dashboards Members
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
ADM-1 | As an admin, I want a persistent left-side navigation workspace shell so I can move between all 20 admin sections predictably, per RFP §3.4. | Sidebar lists all 20 admin sections in the RFP's specified order; active section is visually indicated; sidebar persists across navigation without full-page reload. | - Build the admin app shell with persistent sidebar - Wire client-side routing for all 20 sections (stubs where features aren't built yet) - Apply the re-themed admin visual language from DES-W-3 | Admin | Critical | Medium | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-2 | As an admin, I want a ⌘K global command palette so I can search and act on anything without hunting through the sidebar, per RFP §4.4.1. | ⌘K opens a searchable command palette covering navigation targets and quick actions; typing a member name jumps directly to that Member 360 profile; keyboard-only operation works end-to-end. | - Build the command-palette overlay and fuzzy-search index - Wire navigation and quick-action commands - Wire global search across members as the first data source | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-3 | As an admin, I want an Operations Dashboard home page showing moderation queue depth, donation totals, upcoming events, dues-aging alerts, member growth, and recent audit entries, per RFP §4.5.4. | Dashboard renders all six specified widgets with live data; each widget links through to its full section; loads in under 2 seconds on staging with representative seed data. | - Build each of the six dashboard widgets - Wire each widget's drill-through link - Add role-based dashboard variants for Treasurer, Communications, Pathshala, Events, Super-Admin | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-4 | As an admin, I want a Member 360 view so a member's contact info, family, membership, donations, dues, volunteer hours, Pathshala enrollment, RSVPs, posts, and sign-in audit are all one click away, per RFP §4.5.1. | Member 360 is a tabbed single profile page covering all nine listed data categories; every tab loads without navigating away from the profile; used as the destination for Members & Families, Support, and Moderation sections. | - Build the tabbed Member 360 layout - Wire each of the nine data tabs to its backend source - Link Member 360 as the drill-through target from search, moderation, and support | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-5 | As an admin, I want to bulk-import members via CSV so onboarding JCA's existing congregation doesn't require one-by-one entry, per RFP §4.4.1. | CSV upload validates required columns, previews a diff before commit, reports per-row errors without failing the whole batch, and writes one audit-log entry summarizing the import. | - Build the CSV upload and validation UI - Implement the preview-before-commit step - Implement per-row error reporting and partial-success handling | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-6 | As an admin, I want optimistic locking and real-time presence indicators so two admins editing the same record never silently overwrite each other, per RFP §4.4.1. | A record's version column blocks a stale save with a clear conflict message; a moderation-queue post shows 'X is already reviewing this post' when a second admin opens it concurrently. | - Implement optimistic-locking conflict detection on save - Implement a presence-indicator websocket/polling channel for moderation views - Build the conflict-resolution UI (reload vs. force-save with warning) | Admin, Backend | High | High | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
ADM-7 | As an admin, I want to resolve sign-in support tickets and trigger a password reset for a member so I can help someone locked out without engineering involvement. | Admin can search for a member, view their sign-in audit trail, and trigger a password-reset email or unlock an account, with an audit-log entry recorded for the action. | - Build the sign-in support lookup and action panel inside Member 360 - Wire password-reset trigger to the auth service - Record the support action in the audit log | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S6-S7 (Weeks 11-14) | Ready
Sprint: S6-S7 · Weeks 11-14 · Sprint Complexity: High · Gate: Sprint demo

## Donations and Causes
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DON-1 | As a member or visitor, I want a Causes list with progress bars and quick-give amount chips so giving takes one tap, per the walkthrough's slide 10. | Causes list shows active causes with progress bar, raised-vs-goal, quick-give chips ($51/$108/$251/$501/$1008/custom), a recurring toggle, and the 501(c)(3) badge; donation is available to unauthenticated visitors on web per RFP §3.4. | - Build the Causes list screen with progress bars and quick-give chips - Wire recurring toggle to hand off into the Subscriptions flow - Enable unauthenticated donation on public web | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
DON-2 | As a member, I want an anonymous toggle and memorial/honoree text field on any donation so I can give privately or in someone's memory, per RFP §2.2 privacy-by-default. | Anonymous toggle hides the donor's name from any public recognition surface (Sponsors of the Month, feed); memorial/honoree free-text field appears on the donation form and prints on the receipt when filled. | - Add anonymous toggle and memorial-text field to the donation form - Enforce anonymity across every public recognition surface - Include memorial text on the generated PDF receipt | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
DON-3 | As a member, I want causes tied to upcoming events to automatically rise to the top of the list with a countdown, so event-based giving is prioritized, per RFP §4.1.2. | A cause linked to an event shows a countdown to the event date and an event-tied goal-progress bar; linked causes sort above unlinked causes as the event date approaches, per a configurable prioritization window. | - Implement the event-linked cause sorting/prioritization logic - Build the countdown and event-tied progress-bar UI - Expose the prioritization-window config to admins | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
DON-4 | As a member, I want Jeev Daya as a permanent, always-visible cause dedicated to animal welfare, per RFP §4.1.2. | Jeev Daya appears in the Causes list at all times regardless of event proximity; admin can link partner-organization information to the cause. | - Seed Jeev Daya as a permanent, non-retirable cause - Add partner-organization link fields in the admin cause editor | iOS, Android, Web, Admin | Medium | Low | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
DON-5 | As a member, I want my complete donation history with per-donation receipts and a year-end statement, grouped by year, per the walkthrough's slide 15. | History screen shows a YTD total hero card, year-end statement download, year-pill tabs (current/previous/all years), and monthly grouping with a per-row receipt download. | - Build the Donation History screen with year-pill tabs and monthly grouping - Wire per-row receipt download - Wire the YTD total and year-end statement download | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
DON-6 | As an admin, I want to create, edit, prioritize, and retire causes, and tie causes to events, so the giving catalog stays current. | Cause CRUD supports goal amount, description, event linkage, and manual priority override; retiring a cause removes it from member-facing lists while preserving its donation history. | - Build the Causes & Donations admin section CRUD - Implement the event-linkage control - Implement retire (soft-delete) with history preservation | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S7 (Weeks 13-14) | Ready
Sprint: S7 · Weeks 13-14 · Sprint Complexity: High · Gate: Sprint demo

## Recurring Giving and Subscripti
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
SUB-1 | As a member, I want templated recurring-giving plans (Daily Aarti $11, Bhojanshala $108/mo, Paryushan $2,508/yr) so I can set up giving on autopilot in one tap, per the walkthrough's slide 16. | Set Up New tab shows the three templates plus a custom-amount/frequency option; selecting a template pre-fills amount and frequency and routes to the payment confirmation screen. | - Build the Set Up New subscription screen with templates - Wire template selection to the shared payment-confirmation screen - Create the recurring_subscription record and Stripe Billing subscription on success | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
SUB-2 | As a member, I want to pause, edit the amount, or cancel any recurring subscription in two interactions or fewer, per RFP §2.2's financial-caution principle. | My Subscriptions tab lists active plans with next-charge date and lifetime total; Pause and Edit-Amount actions are one tap plus one confirmation; Cancel is the same two-interaction limit; no silent auto-renewal changes occur. | - Build the My Subscriptions list with Pause/Edit/Cancel actions - Enforce the two-interaction limit in the UI flow - Wire actions to the Stripe Billing subscription API | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
SUB-3 | As a member, I want a one-time gift to offer a 'Make monthly' upgrade path so converting to recurring giving doesn't require starting over. | The Thank You confirmation screen after a one-time gift offers a 'Make monthly' CTA that pre-fills a new recurring subscription with the same amount and cause. | - Add the 'Make monthly' CTA to the Thank You screen - Pre-fill the Set Up New flow from the completed one-time donation | iOS, Android, Web | Medium | Low | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
SUB-4 | As a backend engineer, I want failed-charge recovery (dunning) for recurring subscriptions so a declined card doesn't silently lapse a member's giving. | A failed recurring charge triggers a retry schedule and a notification to the member with a link to update their payment method; after a configurable number of failures the subscription is paused, not silently cancelled. | - Implement Stripe Billing dunning/retry configuration - Wire failed-charge notifications with an update-payment-method deep link - Implement the auto-pause-after-N-failures rule | Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
SUB-5 | As an admin, I want to view, pause, edit, or cancel any member's recurring subscription on their behalf, gated by the two-person rule for cancel. | Subscription Manager component (RFP §4.5.1) is available from Donations & Causes and from Member 360; cancel-on-behalf requires second-admin confirmation; pause and edit-amount do not. | - Build the admin Subscription Manager component - Wire cancel-on-behalf through the two-person confirmation modal - Surface the component in both Donations & Causes and Member 360 | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
Sprint: S8 · Weeks 15-16 · Sprint Complexity: High · Gate: Sprint demo

## Membership Family and Dues
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
MFD-1 | As a member, I want a family-member list with relationship, DOB, and gotra so my whole family's record lives in one place, per the walkthrough's slide 24. | Family cards show Self, Spouse, Children (with Pathshala badge where enrolled), and Parents, each with avatar, relationship, DOB, and gotra/anniversary; + Add Family Member creates a new family_member record. | - Build the Family screen with per-relationship cards - Implement + Add Family Member with the relationship/DOB/gotra form - Wire the Pathshala badge to actual enrollment status | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
MFD-2 | As a member, I want a Pending Dues card with itemized lines and a Pay All Now button, always shown when I owe money, per RFP §4.1.2. | Pending Dues card appears on Home and Family whenever the family's total due is greater than zero, itemizing membership, MJK pass, and Pathshala fee lines; Pay All Now routes through the shared payment-confirmation screen for the full itemized total. | - Build the Pending Dues card component - Wire it to show/hide based on total-due > 0 - Wire Pay All Now to the shared payment-confirmation flow | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
MFD-3 | As a member, I want to see my membership tier, since-date, and renewal date with a renewal payment flow so I never lapse without knowing. | Profile shows tier, since-date, and renewal date; a Manage button opens the renewal payment flow when renewal is due or upcoming; lifetime-tier members see a distinct, non-renewing state. | - Build the membership status card on Profile - Implement the renewal payment flow - Handle the lifetime-tier non-renewing display state | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
MFD-4 | As an admin, I want a family record manager to add, remove, and merge family records with family-level vs. member-level dues toggles, per RFP §4.5.1. | Admin can create, edit, merge, and remove family records; a per-family toggle controls whether dues are calculated at the family level or per individual member; merge preserves both families' donation and dues history. | - Build the Family Record Manager admin component - Implement the merge workflow with history preservation - Implement the family-level vs. member-level dues toggle | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
MFD-5 | As an admin (Treasurer role), I want a dues ledger with running balance and an aging report (30/60/90 days) so overdue dues are visible and actionable, per RFP §4.5.1. | Dues Ledger component shows every issued/paid/comped/waived/refunded entry per family with a running balance; aging report buckets overdue families into 30/60/90-day tiers; a dunning workflow sends templated reminders per bucket. | - Build the Dues Ledger component with running balance - Build the 30/60/90-day aging report - Wire the dunning workflow to the Transactional Template Library | Admin, Backend | High | High | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
MFD-6 | As an admin, I want to issue dues credits or comps with an audit trail, gated by the two-person rule for money, per RFP §2.2. | Credit/comp issuance requires a reason and a second admin's confirmation before it commits; both actors are recorded in the immutable audit log; the family's ledger reflects the credit immediately after confirmation. | - Build the credit/comp issuance form - Wire it through the two-person confirmation modal - Verify the audit-log entry captures both actors and the reason | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S8 (Weeks 15-16) | Ready
Sprint: S8 · Weeks 15-16 · Sprint Complexity: High · Gate: Sprint demo

## Sponsorships and Religious Cale
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
SPN-1 | As a member, I want a Sponsor a Tithi flow with a calendar picker, tiered amounts, and anonymous/memorial options, per the walkthrough's design intent. | Calendar picker shows open vs. booked tithi dates; tiered sponsorship amounts selectable; anonymous toggle and memorial/honoree text available; completed sponsorship writes a sponsorship record linked to the donation. | - Build the Tithi calendar picker with open/booked states - Build the tiered-amount selection UI - Wire completion to create the sponsorship + donation records | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
SPN-2 | As a member, I want Daily Pooja & Abhishek schedules across all five traditions with sponsor recognition, so no tradition is deprioritized, per RFP §2.2's five-traditions-one-sangha principle. | Schedule displays day-by-day pooja/abhishek slots for all five traditions with equal visual prominence; sponsored slots show sponsor recognition (respecting anonymity); sign-in is not required to view, per RFP §4.1.2. | - Build the five-tradition daily schedule view - Wire sponsor-recognition display with anonymity handling - Verify equal visual treatment across all five traditions | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
SPN-3 | As a member, I want a specialized Bhojanshala sponsorship flow with a date picker, three meal-type tiers, and a live meal-count, per the walkthrough's slide 11. | Date picker shows open (available) vs. dimmed (booked) dates; tiers are full lunch/sweet box/snack seva with the RFP's example pricing; anonymous toggle and memorial text available; live count of meals served this month displays on the screen. | - Build the Bhojanshala date picker with open/booked states - Build the three-tier selection UI - Wire the live monthly meal-count display | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
SPN-4 | As a member, I want a Sponsors of the Month view honoring every donor for the current month, with per-sponsor detail and memorial text, per the walkthrough's slide 14. | Pill tabs filter All/Bhojanshala/Festivals; month total raised and sponsor count shown; per-sponsor row shows name (respecting anonymity), what they sponsored, amount, and date; tapping a sponsor opens their public profile. | - Build the Sponsors of the Month list with category tabs - Wire the month-total and sponsor-count summary - Link each sponsor row to the public member-view profile | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
SPN-5 | As an admin, I want a pooja/abhishek schedule editor and a Bhojanshala kitchen calendar so I can assign sponsors, mark slots open/sponsored, and track meal counts across the five traditions, per RFP §4.5.2. | Schedule editor supports a daily slot grid across all five traditions with sponsor assignment; kitchen calendar supports meal-type tier configuration and meal-count tracking; both generate sponsor-recognition feeds for Home and Community. | - Build the pooja/abhishek schedule editor with the five-tradition grid - Build the Bhojanshala kitchen calendar with tier configuration - Wire both to the sponsor-recognition feed generator | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
SPN-6 | As an admin, I want to configure Sponsor a Tithi tiers and open dates, and approve memorial text, so sponsorship offerings stay curated and appropriate. | Admin can configure tier amounts and open/close individual tithi dates; memorial/honoree text submitted by a member enters a review queue before it displays publicly. | - Build the Tithi tier and open-dates configuration UI - Build the memorial-text review queue | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S9 (Weeks 17-18) | Ready
Sprint: S9 · Weeks 17-18 · Sprint Complexity: High · Gate: Sprint demo

## Community Feed and Moderation
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
COM-1 | As a member, I want to see an explicit whitelist disclosure and never see my own pending post appear publicly, so I understand and trust the moderation model, per RFP §2.2. | Feed shows a persistent disclosure that member posts are reviewed before appearing publicly; a submitted post shows a 'pending review' state visible only to its author; no optimistic UI ever displays a pending post to any other user, even momentarily. | - Build the whitelist-disclosure banner on the feed - Implement the author-only pending-post state with strict server-side filtering - Write an automated test proving a pending post never appears in another user's feed response | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
COM-2 | As a member, I want to compose a post and see pinned admin announcements alongside approved member posts, filterable by All/Admin/Members/Youth, per the walkthrough's slide 17. | Compose stub accepts text and media; feed renders pinned admin posts first, then approved member posts chronologically; pill-tab filters work; reactions are available on both post types. | - Build the compose UI with media attachment - Build the feed rendering with pinned-post ordering and filters - Implement reactions | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
COM-3 | As a member, I want to report a post so inappropriate content reaches moderation quickly. | Report action available on every post with a reason selector; a report creates a content_report entry visible in the admin moderation queue with the post automatically flagged. | - Build the report action and reason selector - Wire report submission into the moderation queue | iOS, Android, Web, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
COM-4 | As an admin, I want a moderation queue to approve, decline, edit, or flag member posts with real-time presence indicators, per RFP §2.2 and §4.4.1. | Moderation queue lists pending posts with one-click approve/decline/edit/flag actions; a decline requires a reason returned to the author; presence indicator shows when another admin is already reviewing a given post. | - Build the moderation queue list and action buttons - Implement the decline-with-reason flow - Wire the presence-indicator channel built in ADM-6 | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
COM-5 | As an admin, I want to pin/unpin admin posts and manage badges (Youth, Pathshala) so the feed's structure and member recognition stay curated. | Pin/unpin toggle available on any admin-authored post; badge assignment available per member, visible next to their name on posts and profiles. | - Build the pin/unpin control - Build the badge assignment UI in Member 360 - Render badges next to author names on posts | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
COM-6 | As an admin, I want a reported-content handling workflow so member-flagged posts are triaged distinctly from routine new-post moderation. | Reported posts appear in a distinct queue view with the reporter's reason visible; resolving a report records the outcome and clears it from the queue. | - Build the reported-content queue view - Wire report resolution and outcome recording | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S10 (Weeks 19-20) | Ready
Sprint: S10 · Weeks 19-20 · Sprint Complexity: Medium · Gate: Sprint demo

## Notifications and Messaging
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
NOT-1 | As a backend engineer, I want notifications to fan out from the backend to APNs, FCM, Web Push, and email so every member is reachable regardless of surface or preference, per RFP §3.1. | A single notification-send call fans out to all registered device tokens/channels for the target audience; email fallback fires automatically for users who have declined push; delivery status recorded per channel. | - Implement the APNs and FCM push-sending integration - Implement Web Push sending - Implement the email-fallback rule for push-declined users | Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
NOT-2 | As a member, I want device registration and per-category notification preferences so I control what reaches me and how, including opt-in birthday/anniversary alerts, per RFP §2.2. | Device token registered on app install/sign-in; Profile > Notifications lets a member toggle categories (events, donations, community, Pathshala) per channel; birthday/anniversary notifications are opt-in per family member, off by default. | - Implement device-token registration on install/sign-in - Build the per-category, per-channel preference UI - Implement the per-family-member opt-in for birthday/anniversary | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
NOT-3 | As an admin, I want a notification composer with multi-surface preview so I can see exactly how a push will look before sending, per RFP §4.5.7. | Composer shows a live preview for iOS lock screen, Android notification shade, web push, and email fallback; a deliverability estimate is shown before send; send-now and schedule-for-later both work. | - Build the notification composer with the four-surface preview panel - Wire the deliverability-estimate calculation - Implement send-now and scheduled-send | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
NOT-4 | As an admin, I want a segment builder so I can target a notification by any combination of saved filters, per RFP §4.5.7. | Segment builder combines filters (tab activity, tradition, family role, Pathshala enrollment, membership tier); estimated reach updates live as filters change; segments are saveable and reusable across Notifications and Newsletter. | - Build the segment builder UI with combinable filters - Implement live estimated-reach calculation - Wire saved segments for reuse across Notifications and Newsletter | Admin, Backend | High | High | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
NOT-5 | As an admin, I want a per-notification delivery report with per-surface breakdown so I know whether a message actually reached people, per RFP §4.5.7. | Delivery report shows sent/delivered/opened (where measurable)/action-taken/bounced/opted-out, broken down by iOS/Android/web/email. | - Build the delivery-report aggregation query and view - Implement per-surface breakdown | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
NOT-6 | As an admin, I want a transactional template library for receipts, dues reminders, RSVP confirmations, and sign-in alerts, with an audit trail, per RFP §4.5.7. | Templates are editable per notification type with variable placeholders; every edit is recorded in the audit trail; templates are used by the actual sending code paths, not duplicated inline. | - Build the transactional template editor - Wire template edits to the audit trail - Refactor existing sending code (receipts, dues reminders, RSVP confirmations) to use the template library | Admin, Backend | Medium | Medium | Phase 1 — v1.0 (initial launch) | S11 (Weeks 21-22) | Ready
Sprint: S11 · Weeks 21-22 · Sprint Complexity: High · Gate: Sprint demo

## Pathshala
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
PS-1 | As a parent, I want a children's class hub showing enrolled children with class badges, today's lesson, and term-fee status, per the walkthrough's slide 18. | Pathshala hub lists each enrolled child with class badge, today's lesson and materials download, term schedule, term-fee status, teacher contact, and attendance streak. | - Build the Pathshala hub layout with per-child cards - Wire today's lesson and materials download - Wire term-fee status to the dues ledger | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
PS-2 | As a parent, I want a teacher-contact and parent-feedback flow so I can reach my child's teacher directly. | Teacher contact info is visible per class; a feedback form routes to the assigned teacher's admin queue. | - Display teacher contact info per class - Build the parent-feedback form and routing | iOS, Android, Web, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
PS-3 | As an admin (Pathshala coordinator), I want enrollment management, class roster, and term-fee status tracking so I run the program without spreadsheets, per RFP §3.4. | Admin can enroll/withdraw a child, view the class roster, and see term-fee status per enrollment; a Pathshala coordinator role can do this without access to refunds, per RFP §4.4.1's granular-permissions example. | - Build enrollment management CRUD - Build the class roster view - Verify the Pathshala coordinator role has scoped permissions (roster edit, no refund access) | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
PS-4 | As an admin, I want lesson and material publishing plus teacher account assignment so class content flows through the same authoring tools as everything else. | Admin can publish a lesson with attached materials to a class; teacher accounts are assignable to classes with scoped access to only their own roster and lessons. | - Build the lesson/material publishing UI - Build teacher-account assignment with scoped access | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
Sprint: S12 · Weeks 23-24 · Sprint Complexity: Medium · Gate: Sprint demo

## Volunteers and Seva
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
VOL-1 | As a member, I want to browse open volunteer opportunities and sign up, plus see my lifetime seva-hour total, per the walkthrough's slide 19. | Opportunity cards show name, commitment, when, and category (Bhojanshala, Pathshala, Festival, Setup/Cleanup); sign-up is one tap; lifetime seva-hour total is displayed read-only. | - Build the opportunity list and category filters - Implement one-tap sign-up - Display the read-only lifetime seva-hour total | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
VOL-2 | As a Youth member, I want a group-volunteering sign-up option so friends can commit to an opportunity together. | Group sign-up lets a Youth member add multiple names to one opportunity in a single submission. | - Build the group sign-up flow for Youth-tagged opportunities | iOS, Android, Web, Backend | Low | Low | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
VOL-3 | As an admin, I want to create volunteer opportunities, manage sign-ups, and log hours (admin-entered in v1.0), per RFP §3.4 item 10. | Admin can create/edit/retire opportunities and view sign-ups; admin-entered hour logging updates a member's lifetime total immediately; member-entered hour logging is explicitly deferred to Phase 2 consideration. | - Build opportunity CRUD and sign-up management - Build the admin hour-logging form - Document member-entry deferral in the module notes | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
VOL-4 | As an admin, I want a volunteer-recognition export for Service Awards so seva contributions feed into the Phase 2 recognition program. | Export produces a CSV of lifetime seva hours per member, filterable by date range, suitable as input to the Phase 2 Service Awards selection process. | - Build the volunteer-recognition CSV export | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S12 (Weeks 23-24) | Ready
Sprint: S12 · Weeks 23-24 · Sprint Complexity: Medium · Gate: Sprint demo

## Live Darshan
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
LD-1 | As a member, I want live video from each of the five Jain traditions with a dark-mode UI so I can join darshan remotely, per the walkthrough's slide 7 (Astapadji explicitly excluded). | Five shrine streams selectable (Mahavir, Adinath, Upashray, Shrimad, Dadawadi); live indicator with viewer count; dark-mode UI throughout; Astapadji is not present as a stream option. | - Build the five-shrine stream selector UI in dark mode - Wire live-indicator and viewer-count display - Confirm Astapadji exclusion in the admin stream-source config | iOS, Android, Web, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
LD-2 | As a mobile user, I want Picture-in-Picture and AirPlay/Cast so I can keep watching darshan while using my phone or cast it to a TV, per RFP §4.1.2. | PiP works on iOS and Android; AirPlay works on iOS to an Apple TV; Google Cast works on Android to a Chromecast; all three build on the ARCH-2 spike's proven configuration. | - Implement PiP using the proven react-native-video v6 config - Implement AirPlay support on iOS - Implement Google Cast support on Android | iOS, Android | Critical | High | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
LD-3 | As a web visitor, I want HLS playback with a low-latency option so I can watch darshan from a browser without an app install, per RFP §4.1.2. | Web player supports standard HLS playback and a low-latency mode toggle; playback works on the major desktop and mobile browsers without a plugin. | - Integrate an HLS.js-based web player with low-latency mode - Cross-browser test on Chrome, Safari, Firefox, and mobile Safari/Chrome | Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
LD-4 | As an admin, I want to configure the HLS stream URL, fallback, and on/off scheduling per tradition, and monitor stream health, per RFP §3.4 item 14. | Admin can set primary and fallback HLS URLs per tradition, schedule on/off windows, and see a stream-health status indicator (up/down/degraded) with recent uptime history. | - Build the per-tradition stream-source configuration UI - Implement on/off scheduling - Build the stream-health monitoring dashboard | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
LD-5 | As a member, I want a notification 15 minutes before evening aarti so I don't miss it, per the walkthrough's slide 4. | A scheduled notification fires 15 minutes before each tradition's configured evening aarti time, respecting the member's notification preferences; tapping it deep-links directly into that tradition's Live Darshan stream. | - Implement the scheduled aarti-reminder notification job - Wire the deep link into the correct tradition's stream | iOS, Android, Web, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
Sprint: S13 · Weeks 25-26 · Sprint Complexity: Very High · Gate: Sprint demo

## Admin Governance and Operations
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
GOV-1 | As a Super-Admin, I want an immutable, filterable audit log retained for seven years so every state-changing operation is reviewable, per RFP §4.4.1 and §4.5.3. | Audit log viewer filters by actor, action type, target record, and time range; entries cannot be edited or deleted through any application code path; export available for board/audit-committee review. | - Build the Audit Log viewer with the four filter dimensions - Enforce immutability at the database/application layer - Build the audit-log export | Admin, Backend | Critical | High | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-2 | As an admin, I want a reusable two-person confirmation modal for every money-moving operation so the two-person rule is enforced consistently everywhere, per RFP §4.4.1. | One shared component handles refunds, dues comps, manual donation entry, and subscription cancel-on-behalf; the initiating admin's request is visible to a second admin who must authenticate to confirm; both signatures are captured in the audit log. | - Build the shared two-person confirmation modal component - Wire it into refunds, dues comps, manual donation entry, and subscription cancellation - Verify both actors are captured in every resulting audit-log entry | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-3 | As an admin, I want a soft-delete trash so any deleted record is recoverable for 30 days before a scheduled hard-delete, per RFP §4.4.1. | Every deletable record type appears in a searchable trash view within its section; Restore returns it to its prior state; after 30 days an automated job hard-deletes tombstoned records, with legal-retention exceptions for donation records. | - Build the soft-delete trash view per section - Implement the scheduled hard-delete job with the donation-record retention exception - Verify restore returns a record to its exact prior state | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-4 | As a Super-Admin, I want a feature-flag console for staged rollout (staff, committee, percentage, full) so new features ship safely post-launch, per RFP §4.4.2. | Feature flags can be toggled through the four rollout stages; each flag change is audit-logged; a flagged feature is visible only to the intended population at each stage. | - Build the feature-flag console UI - Implement the four-stage rollout evaluation logic - Wire flag changes to the audit log | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-5 | As a Super-Admin, I want a maintenance-mode toggle with a configurable banner and ETA so planned downtime is communicated clearly, per RFP §4.4.2. | Toggling maintenance mode displays a banner with a custom message and ETA across all member-facing surfaces; toggle is Super-Admin only and audit-logged. | - Build the maintenance-mode toggle and banner content editor - Wire the banner to display across iOS, Android, and web | Admin, iOS, Android, Web, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-6 | As a Super-Admin, I want an encrypted integration-credentials vault so payment, push, email, and streaming secrets are managed centrally and never exposed in plaintext, per RFP §4.5.3. | Credentials vault stores references to Secret Manager entries, not raw secrets, in the database; only Super-Admin role can view/edit; every credential rotation is audit-logged. | - Build the credentials vault UI backed by Secret Manager references - Enforce Super-Admin-only access - Wire rotation events to the audit log | Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-7 | As a Super-Admin, I want backup/restore visibility with a mandatory confirmation step so I can verify backups are happening and recover from a bad state if needed, per RFP §4.4.2. | Admin sees the timestamp of the last successful backup; triggering a restore-from-backup requires explicit Super-Admin confirmation and writes an audit-log entry; a scheduled restore drill can be configured. | - Build the backup-status visibility panel - Build the restore-from-backup workflow with mandatory confirmation - Configure automated daily backups on Cloud SQL | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
GOV-8 | As a Super-Admin, I want a dedicated System-health panel showing backend status, queue depths, third-party-integration health, and recent error rates, with on-call paging, per RFP §4.5.4. | System-health panel (distinct from the summary widget on the general Operations Dashboard) shows live backend service status, Celery queue depth, payment/push/email/streaming integration health, and recent error-rate trend; a configurable threshold breach triggers an on-call page. | - Build the System-health panel with the four live status categories - Wire the recent-error-rate trend chart - Configure threshold-based on-call paging | Admin, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S13 (Weeks 25-26) | Ready
Sprint: S13 · Weeks 25-26 · Sprint Complexity: High · Gate: Sprint demo

## Public Web and SEO
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
SEO-1 | As a prospective member or journalist, I want the public website indexable by search engines so I can find JCA when I search, per RFP §3.2 and §4.1.3. | Every public page has proper meta tags, Open Graph tags, and a canonical URL; an XML sitemap and robots.txt are published and correct; Google and Bing site verification is completed. | - Implement meta tags, Open Graph, and canonical URLs across public pages - Generate and publish the XML sitemap and robots.txt - Complete Google Search Console and Bing Webmaster verification | Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S14 (Weeks 27-28) | Ready
SEO-2 | As a search engine, I want structured data (Schema.org) on events, religious services, and the organization so rich results can render for JCA content. | Event pages emit Event schema; the organization page emits Organization/NGO schema; religious-service pages emit appropriate structured data; validated with Google's Rich Results Test. | - Implement Schema.org Event markup - Implement Schema.org Organization markup - Validate all structured data with Google's Rich Results Test | Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S14 (Weeks 27-28) | Ready
SEO-3 | As a Core Web Vitals budget owner, I want public pages to meet performance budgets so search ranking and elder-device usability aren't harmed by a slow site. | LCP, INP, and CLS meet 'Good' thresholds on Lighthouse for the homepage, an event page, and the donate page on a throttled mobile profile; a performance budget is enforced in CI. | - Establish Core Web Vitals budgets and CI enforcement - Optimize the homepage, event page, and donate page against the budget - Document the budget in the engineering practices doc | Web | High | Medium | Phase 1 — v1.0 (initial launch) | S14 (Weeks 27-28) | Ready
SEO-4 | As an unauthenticated visitor, I want to donate and sign up for the mailing list without creating an account, per RFP §3.2. | Donation and mailing-list signup flows work fully without sign-in on the public site; a post-donation prompt offers account creation without requiring it. | - Verify unauthenticated donation flow works end-to-end on public web - Add the optional post-donation account-creation prompt | Web, Backend | Critical | Low | Phase 1 — v1.0 (initial launch) | S14 (Weeks 27-28) | Ready
Sprint: S14 · Weeks 27-28 · Sprint Complexity: Medium · Gate: Sprint demo

## Localization and Accessibility
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
L10N-1 | As a backend engineer, I want the centralized translation catalog wired end-to-end so English content renders correctly on all four surfaces from one source, per RFP §3.1 and §5.2. | All user-facing strings route through the localization_string catalog; English is fully populated; a string change in the catalog reflects on all surfaces without a client redeploy (cache-invalidated). | - Wire the localization_string catalog into all four surfaces' rendering layer - Populate English strings for every screen - Implement cache invalidation on catalog updates | iOS, Android, Web, Admin, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S15 (Weeks 29-30) | Ready
L10N-2 | As a translator, I want Hindi and Gujarati scaffolding wired (infrastructure present, not yet populated) so Phase 2 translation work has no engineering dependency. | Locale switching mechanism exists and is testable end-to-end with placeholder Hindi/Gujarati strings; the full population of real translations is explicitly out of scope for this sprint and deferred to Phase 2. | - Implement locale-switching infrastructure across all surfaces - Verify with placeholder Hindi/Gujarati content - Document the Phase 2 population plan | iOS, Android, Web, Admin, Backend | High | Low | Phase 1 — v1.0 (initial launch) | S15 (Weeks 29-30) | Ready
L10N-3 | As a member, I want Sanskrit/Prakrit terminology and diacritics preserved verbatim in every locale so religious accuracy is never lost in translation, per RFP §5.2. | Terms like anumodana, swamivatsalya, dāna, and pratikraman render identically and with correct diacritics regardless of active locale; font stack verified to render diacritics correctly on all platforms. | - Audit font rendering of diacritics across iOS, Android, and web - Mark Sanskrit/Prakrit terms as non-translatable in the catalog schema - Verify verbatim rendering across all three active/scaffolded locales | iOS, Android, Web, Backend | Critical | Low | Phase 1 — v1.0 (initial launch) | S15 (Weeks 29-30) | Ready
L10N-4 | As an accessibility auditor, I want a per-surface accessibility audit embedded in the Definition of Done so WCAG 2.1 AA is verified, not assumed, per RFP §4.1.1. | Every shipped screen passes an automated accessibility scan plus a manual screen-reader pass (VoiceOver, TalkBack, and a desktop screen reader for web); the Skip to Content equivalents from Discovery item DISC-6 are implemented on all three surfaces; results logged per screen. | - Integrate automated accessibility scanning into CI - Perform manual VoiceOver/TalkBack/screen-reader passes on representative screens - Implement the three platform-native Skip to Content equivalents | iOS, Android, Web | Critical | Medium | Phase 1 — v1.0 (initial launch) | S15 (Weeks 29-30) | Ready
L10N-5 | As an admin, I want a context-aware translation-catalog management interface so I can manage strings without touching code. | Admin Settings section lists every translation key with its English value and locale variants; edits save immediately and propagate per L10N-1's cache-invalidation mechanism. | - Build the translation-catalog management UI in admin Settings - Wire edits to immediate propagation | Admin, Backend | Medium | Low | Phase 1 — v1.0 (initial launch) | S15 (Weeks 29-30) | Ready
Sprint: S15 · Weeks 29-30 · Sprint Complexity: Medium · Gate: Sprint demo

## Security Testing and QA
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
SEC-1 | As a developer, I want TLS 1.2+ enforced everywhere with strict ATS/NSC/HSTS/CSP so all network traffic is encrypted and hardened, per RFP §5.1. | All traffic redirects to TLS 1.2+; iOS App Transport Security is configured strictly with no exceptions; Android Network Security Config is strict; web enforces HSTS and a strict Content Security Policy by default. | - Configure strict ATS on iOS - Configure strict Network Security Config on Android - Configure HSTS and CSP headers on web/backend | iOS, Android, Web, Backend | Critical | Medium | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
SEC-2 | As a developer, I want at least 70% line coverage on business-logic modules across all surfaces, per RFP §5.3. | Coverage reports show >=70% on business-logic modules for backend, web, admin, and mobile; coverage gate enforced in CI, blocking merge on regression. | - Audit current coverage gaps across all four surfaces - Write tests to close gaps to the 70% threshold - Add the coverage gate to CI | Backend, Web, Admin, iOS, Android | Critical | High | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
SEC-3 | As a QA engineer, I want end-to-end tests for the five primary flows (sign-in, donate, dues payment, post-to-community, moderate-a-post) so critical paths never regress silently, per RFP §5.3. | E2E suite (Playwright/Detox or equivalent) covers all five flows on the applicable surfaces; suite runs on every PR affecting those flows and blocks merge on failure. | - Write the sign-in and donate E2E tests - Write the dues-payment, post-to-community, and moderate-a-post E2E tests - Wire the suite into CI as a merge-blocking check | Backend, Web, Admin, iOS, Android | Critical | High | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
SEC-4 | As a developer, I want rate limiting on public-facing APIs and dependency-vulnerability scanning in CI so abuse and known CVEs are caught automatically, per RFP §5.1. | Public API routes are IP-rate-limited with a configurable threshold returning 429 when exceeded; every PR runs a dependency scan that blocks merge on a Critical finding; a scheduled weekly full scan runs against main. | - Implement rate limiting on public API routes - Wire dependency scanning (e.g. Dependabot/Snyk) into CI - Configure the scheduled weekly full scan | Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
SEC-5 | As JCA, I want a third-party penetration test conducted before Phase 1 launch with all High and Critical findings remediated, per RFP §5.1 and §6.1.1. | An independent third-party pen test is completed against the staging environment covering all four surfaces and the backend; every High and Critical finding is remediated and re-verified before the Phase 1 launch gate. | - Engage and scope the third-party pen-test vendor - Triage and remediate every High/Critical finding - Re-verify remediations and file the final pen-test report as a Phase 1 deliverable | Backend, Web, Admin, iOS, Android | Critical | Very High | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
SEC-6 | As a member, I want to request full deletion of my account and personal data, with donation records de-linked but IRS-retained, per RFP §5.1. | A data-deletion request from Profile > Settings removes personally identifying data from the platform within a defined SLA; donation records remain in JCA's accounting system for IRS-compliance retention but are de-linked from any identifying profile. | - Build the data-deletion request flow - Implement the de-linking logic for retained donation records - Document the deletion SLA and retention exception in the privacy policy | iOS, Android, Web, Backend | High | Medium | Phase 1 — v1.0 (initial launch) | S16-S17 (Weeks 31-34) | Ready
Sprint: S16-S17 · Weeks 31-34 · Sprint Complexity: High · Gate: Pen-test report delivered; High/Critical remediation tracked

## Store and Launch Readiness
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
LAUNCH-1 | As the vendor, I want the iOS App Store submission package assembled (Privacy Manifest, Nutrition Label, screenshots) so review can begin, per RFP §5.4. | App Privacy Manifest and Privacy Nutrition Label completed accurately; five screenshots per required device size prepared; listing copy drafted and approved by JCA; JCA's developer account used for submission. | - Complete the App Privacy Manifest and Nutrition Label - Produce screenshots for all required device sizes - Draft and get JCA sign-off on App Store listing copy | iOS | Critical | Medium | Phase 1 — v1.0 (initial launch) | S18-S19 (Weeks 35-38) | Ready
LAUNCH-2 | As the vendor, I want the Google Play submission package assembled (Data Safety form, content rating, feature graphic) so review can begin, per RFP §5.4. | Data Safety form completed accurately; content rating questionnaire submitted; feature graphic and store-listing screenshots prepared; JCA's Play Console account used for submission. | - Complete the Data Safety form - Submit the content-rating questionnaire - Produce the feature graphic and store screenshots | Android | Critical | Medium | Phase 1 — v1.0 (initial launch) | S18-S19 (Weeks 35-38) | Ready
LAUNCH-3 | As a beta tester (JCA committee), I want TestFlight and Play Internal Testing distribution before public release so issues are caught pre-launch, per RFP §6.1.1. | A build is distributed via TestFlight to the JCA committee and via Play Internal Testing to the same group; feedback is collected and triaged before proceeding to public submission. | - Distribute via TestFlight to the JCA committee - Distribute via Play Internal Testing to the same group - Triage and resolve pre-launch feedback | iOS, Android | Critical | Medium | Phase 1 — v1.0 (initial launch) | S18-S19 (Weeks 35-38) | Ready
LAUNCH-4 | As the vendor, I want DNS/SSL configured for the public web and the admin subdomain so both are reachable at their production URLs, per RFP §5.4. | nyjaincenter.org resolves to the production web app with valid SSL; admin.nyjaincenter.org resolves to the admin app with valid SSL and optional IP allowlisting configured if requested by JCA. | - Coordinate DNS transfer/configuration with JCA's existing registrar - Configure SSL for both the public and admin domains - Configure optional IP allowlisting for the admin subdomain | Web, Admin | Critical | Low | Phase 1 — v1.0 (initial launch) | S18-S19 (Weeks 35-38) | Ready
LAUNCH-5 | As JCA, I want App Store and Google Play approval achieved and the admin utility in daily production use, so Phase 1 formally clears its acceptance gate, per RFP §6.2. | iOS app is approved and live on the App Store; Android app is approved and live on Google Play; public web is publicly accessible; admin utility is in active daily use by JCA staff; JCA project committee signs off on every surface. | - Submit both store builds for review and respond to any reviewer feedback - Confirm public web accessibility and admin daily-use handoff - Collect JCA project committee sign-off across all four surfaces | iOS, Android, Web, Admin | Critical | Medium | Phase 1 — v1.0 (initial launch) | S18-S19 (Weeks 35-38) | Ready
Sprint: S18-S19 · Weeks 35-38 · Sprint Complexity: High · Gate: Phase 1 acceptance gate — App Store approved, Play Store approved, public web live, admin in production (RFP §6.2)

## Governance and Documents
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
GOVD-1 | As a member, I want a membership-gated meeting-minutes archive with chronological browse, full-text search, and PDF download, per RFP §4.2. | Board / Executive Committee / General Body minutes are browsable chronologically, gated to signed-in members, full-text searchable, and downloadable as PDF. | - Build the gated meeting-minutes archive UI - Wire full-text search over minutes content - Wire PDF download per minute | iOS, Android, Web, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S20 (Weeks 39-40) | Ready
GOVD-2 | As an admin, I want to upload, tag, version, redact, and publish meeting minutes with gating control, per RFP §4.2. | Admin uploads a PDF, tags meeting type and date, can redact sections before publish, versions the document, and controls which membership tiers can view it. | - Build the minutes upload and tagging UI - Implement version control and redaction workflow - Wire the gating-rule control (uses the tier-based default from Discovery item DISC-5) | Admin, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S20 (Weeks 39-40) | Ready
GOVD-3 | As a member, I want to browse and search published JCA Policies so I understand the rules governing facility use, membership, and conduct, per RFP §4.2. | Policies are browsable and searchable, public to members without additional gating. | - Build the Policies browse/search UI - Wire admin authoring, versioning, and publish for policy documents | iOS, Android, Web, Admin, Backend | Medium | Low | Phase 2 — v1.5 (should-have follow-on release) | S20 (Weeks 39-40) | Ready
GOVD-4 | As a member, I want a long-form Credits & History narrative of the Center's founding, milestones, and restoration efforts, per RFP §4.2. | History page renders a CMS-authored narrative with images and a timeline component. | - Build the Credits & History page with timeline component - Build the CMS-style editor for images and timeline entries | iOS, Android, Web, Admin, Backend | Low | Low | Phase 2 — v1.5 (should-have follow-on release) | S20 (Weeks 39-40) | Ready
Sprint: S20 · Weeks 39-40 · Sprint Complexity: Medium · Gate: Sprint demo

## Library Jinvani and Lectures
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
LIB-1 | As a member, I want a searchable library of Jain scriptures, commentaries, and children's editions with continue-reading state, per the walkthrough's slide 26. | Search covers full text of all catalog PDFs; tabs for All/Agam Sutras/Commentaries/Children/Bookmarks; a Continue Reading hero shows the last-read position (e.g. 'Tattvārtha Sūtra, p.84/312'). | - Build the library catalog browse and tab UI - Implement the Continue Reading state tracking - Stand up Meilisearch and index the PDF catalog for full-text search | iOS, Android, Web, Backend | High | High | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
LIB-2 | As a member, I want audio versions of texts like Samayika so I can listen rather than read. | Audio playback available for tagged catalog entries; offline download available on mobile per RFP §4.2. | - Build the audio player component - Implement offline audio download on mobile | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
LIB-3 | As a member, I want a Pravachan (lecture) archive organized by topic, speaker, and date so I can find teachings relevant to me, per RFP §4.2. | Lecture archive is browsable/filterable by topic, speaker, and date; audio/video playback with offline audio download on mobile; transcript available where uploaded. | - Build the Pravachan archive browse/filter UI - Implement offline audio download - Wire transcript display where available | iOS, Android, Web, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
LIB-4 | As a member, I want to browse the physical/digital library catalog, reserve a physical book, and download a licensed digital book, per RFP §4.2. | Catalog distinguishes physical vs. digital availability; reservation queue for physical books; digital download respects license restrictions. | - Build the catalog browse with physical/digital distinction - Implement the physical-book reservation queue - Implement license-gated digital download | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
LIB-5 | As an enrolled Pathshala family, I want a digital textbook library with grade-level browse, offline download, and parental controls, per RFP §4.2. | Pathshala Books section is gated to enrolled families; browsable by grade level; offline download available; parental controls restrict access appropriate to the child's grade. | - Build the Pathshala Books grade-level browse UI - Implement offline download - Implement parental controls | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
LIB-6 | As an admin, I want catalog management, reservation-queue handling, and license tracking for the library, plus per-grade textbook upload and download analytics for Pathshala Books, per RFP §4.2. | Admin manages the full library and Pathshala Books catalogs, including upload, tagging (tradition/language/topic), reservation approval, license tracking, and download analytics. | - Build the library and Pathshala Books admin CRUD - Build the reservation-queue management UI - Build license tracking and download analytics reporting | Admin, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S21-S22 (Weeks 41-44) | Ready
Sprint: S21-S22 · Weeks 41-44 · Sprint Complexity: High · Gate: Sprint demo

## Directory Travel and Facility B
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
DIR-1 | As a member, I want a Business Directory of member-owned Jain businesses so I can support the sangha economically, per the walkthrough's slide 27. | Directory is category-filterable, shows sangha-discount tags where applicable, and lets a member list their own business for free. | - Build the Business Directory browse/filter UI - Build the + List Your Business submission flow | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S23 (Weeks 45-46) | Ready
DIR-2 | As a traveling member, I want to find Jain centers and pure-veg restaurants nationwide, per the walkthrough's slide 29. | Combined Centers/Restaurants/Map view lets a member find nearby centers and restaurants with Jain-friendly badges; tapping a pin opens directions in the device's maps app. | - Build the Centers/Restaurants combined directory with map view - Wire directions deep-linking to native maps apps | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S23 (Weeks 45-46) | Ready
DIR-3 | As a member, I want to reserve JCA halls with member-rate pricing and see a booking-policy card, per the walkthrough's slide 28. | Date picker shows the three facilities with member-rate pricing; booking-policy card (deposit percentage, refundability, pure-veg-only rule) is displayed before booking; Book routes to the shared payment-confirmation screen for the deposit. | - Build the Facility Booking date picker and facility selector - Build the booking-policy card - Wire deposit payment through the shared confirmation screen | iOS, Android, Web, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S23 (Weeks 45-46) | Ready
DIR-4 | As an admin, I want to approve/decline facility bookings with a calendar-conflict view and deposit tracking, per RFP §3.4 item 11. | Admin sees pending booking requests with the calendar-conflict view from CAL-5 overlaid; approve/decline actions available; deposit paid/outstanding status tracked per booking. | - Build the booking approval queue - Reuse the calendar-conflict view for facility bookings - Wire deposit-status tracking | Admin, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S23 (Weeks 45-46) | Ready
DIR-5 | As an admin, I want to approve member-submitted Business Directory and Restaurant listings so directory quality stays curated, per RFP §3.4 item 16. | Submitted listings enter a review queue; approve/decline with a reason; approved listings appear live immediately. | - Build the listing review queue - Wire approve/decline actions | Admin, Backend | Medium | Low | Phase 2 — v1.5 (should-have follow-on release) | S23 (Weeks 45-46) | Ready
Sprint: S23 · Weeks 45-46 · Sprint Complexity: Medium · Gate: Sprint demo

## Recognition Programs
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
REC-1 | As a member, I want to nominate someone for a Service Award and see award recipients and ceremony info, per RFP §4.2. | Nomination form is available to members; recipient list and ceremony info are publicly viewable once published. | - Build the nomination submission form - Build the recipient/ceremony-info display | iOS, Android, Web, Backend | Medium | Low | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
REC-2 | As an admin (selection committee), I want nomination intake and selection-committee tooling so the award process is organized and fair, per RFP §4.5. | Admin sees all nominations with eligibility criteria checked; a selection-committee scoring/voting tool aggregates decisions; approved recipients publish to the member-facing recipient list. | - Build the nomination intake and eligibility-check view - Build the selection-committee tooling - Wire recipient publishing | Admin, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
REC-3 | As a major donor, I want a Lifetime Supporter Program with perpetual profile recognition and anniversary acknowledgements, per RFP §4.2. | Lifetime Supporters have a distinct, perpetual public listing; anniversary acknowledgements trigger automatically on the giving anniversary date. | - Build the Lifetime Supporter public listing - Implement the anniversary-acknowledgement trigger | iOS, Android, Web, Backend | Low | Low | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
REC-4 | As an admin, I want recognition-rule and perpetual-listing management for the Lifetime Supporter Program, per RFP §4.5. | Admin configures the qualifying threshold and rule set for Lifetime Supporter status; perpetual listings are maintained without manual re-entry each year. | - Build the recognition-rule configuration UI - Automate perpetual-listing maintenance | Admin, Backend | Low | Low | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
Sprint: S24 · Weeks 47-48 · Sprint Complexity: Medium · Gate: Sprint demo

## Youth and YJA
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
YTH-1 | As a Youth-age member (13-25), I want a dedicated Youth section with programming, mentorship, and social events distinct from Pathshala and YJA Programs, per Discovery item DISC-7. | Youth section is age-gated per the DISC-7 resolution; content is distinct from both Pathshala (under-18 classes) and YJA Programs (18-25 national programming). | - Build the Youth section UI and content model - Implement age-gating per the DISC-7 resolution | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
YTH-2 | As a YJA-age member, I want YJA programming (events, registration links, contact info) syndicated into the app, per RFP §4.2. | YJA events appear in the Calendar with a distinct YJA category; registration links route to YJA's own registration system; YJA contact info is discoverable. | - Build the YJA event syndication feed - Add the YJA event category to the Calendar filter set | iOS, Android, Web, Backend | Low | Low | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
YTH-3 | As an admin, I want age-gating configuration and youth-committee tools so Youth content stays appropriately scoped, per RFP §4.5. | Admin configures the age-gating rule (self-attested at signup, parental consent under 18 per DISC-7); youth-committee members get scoped access to author Youth-section content. | - Build the age-gating configuration UI - Build scoped youth-committee content-authoring access | Admin, Backend | Medium | Low | Phase 2 — v1.5 (should-have follow-on release) | S24 (Weeks 47-48) | Ready
Sprint: S24 · Weeks 47-48 · Sprint Complexity: Medium · Gate: Sprint demo

## Past Events and Gallery
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
PEG-1 | As a member, I want an auto-generated Past Events archive with photo links, attendance counts, and donor recognition, per RFP §4.1.2 and §4.2. | Any event past its end date auto-populates into the Past Events archive with a link to its Gallery album, final attendance count, and donor-recognition summary if sponsored. | - Implement the auto-generation trigger on event completion - Build the Past Events archive browse UI - Wire Gallery album and donor-recognition linking | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
PEG-2 | As a member, I want an album-organized photo/video gallery searchable by year and event, per the walkthrough's slide 21. | Hero album shows the most recent festival; album grid organized by event with a year filter; tapping an album opens a masonry grid; video albums show a play overlay. | - Build the gallery hero and album-grid layout - Implement the year filter - Build the masonry-grid album detail view with video play overlay | iOS, Android, Web, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
PEG-3 | As an admin, I want to curate featured entries in the auto-generated Past Events archive so the most significant events get prominence, per RFP §4.2. | Admin can pin/feature specific past events above the auto-generated chronological order. | - Build the featured-entry curation control | Admin, Backend | Low | Low | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
Sprint: S25 · Weeks 49-50 · Sprint Complexity: Medium · Gate: Sprint demo

## Reports and Analytics v2
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
RPT-1 | As a Treasurer, I want donor cohort analysis and retention metrics so I understand giving patterns beyond raw totals, per RFP §4.2. | Report segments donors by cohort (first-year, returning, lapsed) and shows retention rate trend over time; exportable as CSV and PDF. | - Build the donor cohort segmentation query and report view - Build the retention-trend visualization - Wire CSV/PDF export | Admin, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
RPT-2 | As a Treasurer, I want a dues-aging trend report and an events chair wants an event-attendance trend report, so both roles see change over time, not just a snapshot, per RFP §4.2. | Dues-aging trend shows the 30/60/90-day buckets over time; attendance trend shows RSVP and check-in rates across events over time; both exportable. | - Build the dues-aging trend report - Build the event-attendance trend report | Admin, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
RPT-3 | As an admin, I want demographic breakdowns in reporting so program planning can be informed by who's actually participating, per RFP §4.2. | Reports can break down participation by age band, family role, and tradition, respecting the privacy-by-default principle (no individually identifying data exposed in aggregate views). | - Build the demographic-breakdown reporting view - Verify aggregate-only exposure, no individual PII in the report output | Admin, Backend | Low | Medium | Phase 2 — v1.5 (should-have follow-on release) | S25 (Weeks 49-50) | Ready
Sprint: S25 · Weeks 49-50 · Sprint Complexity: Medium · Gate: Sprint demo

## Hindi and Gujarati Localization
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
L10N2-1 | As a Hindi- or Gujarati-speaking member, I want the full app translated into my language across every surface, per RFP §4.2 and §5.2. | Every string in the localization_string catalog has a reviewed Hindi and Gujarati value; switching locale on any surface renders fully translated content with no English fallback strings remaining. | - Populate Hindi translations for the full catalog - Populate Gujarati translations for the full catalog - Audit for any remaining untranslated/fallback strings | iOS, Android, Web, Backend | High | High | Phase 2 — v1.5 (should-have follow-on release) | S26 (Weeks 51-52) | Ready
L10N2-2 | As an admin, I want a reviewer workflow for translation submissions so quality is verified before a translation goes live, per RFP §5.2. | A submitted translation enters a pending-review state; a designated reviewer approves or rejects with comments before it becomes the live value for that locale. | - Build the translation submission and review-queue workflow - Wire approve/reject with reviewer comments | Admin, Backend | High | Medium | Phase 2 — v1.5 (should-have follow-on release) | S26 (Weeks 51-52) | Ready
L10N2-3 | As a translator, I want a context-aware editing interface showing where a string appears in the app so I can translate accurately, per RFP §5.2. | Translator UI shows a screenshot or screen-context preview alongside each string being translated; Sanskrit/Prakrit terms are visibly locked as non-translatable per L10N-3. | - Build the context-aware translator interface with screen previews - Enforce the non-translatable-term lock in the UI | Admin, Backend | Medium | Medium | Phase 2 — v1.5 (should-have follow-on release) | S26 (Weeks 51-52) | Ready
Sprint: S26 · Weeks 51-52 · Sprint Complexity: Medium · Gate: Sprint demo

## v1.5 Hardening and Release
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
HARD1-1 | As JCA, I want an updated third-party penetration test covering the v1.5 surface area so new Phase 2 features are security-verified before release, per RFP §6.1.2. | Pen test covers every Phase 2 feature (gated documents, library/Jinvani, directory, facility booking, recognition programs); all High/Critical findings remediated before the Phase 2 gate. | - Scope and execute the v1.5 pen test - Remediate and re-verify all High/Critical findings | Backend, Web, Admin, iOS, Android | Critical | High | Phase 2 — v1.5 (should-have follow-on release) | S27 (Weeks 53-54) | Ready
HARD1-2 | As JCA, I want updated test coverage maintaining the v1.0 thresholds across all Phase 2 features, per RFP §6.1.2. | Business-logic coverage stays >=70% including all new Phase 2 modules; E2E suite extended to cover at least one Phase 2 critical flow (e.g. gated minutes access). | - Extend unit/integration test coverage to Phase 2 modules - Add a Phase 2 E2E flow to the existing suite | Backend, Web, Admin, iOS, Android | Critical | Medium | Phase 2 — v1.5 (should-have follow-on release) | S27 (Weeks 53-54) | Ready
HARD1-3 | As the vendor, I want store updates for the v1.5 release submitted and approved on both stores, per RFP §6.1.2. | iOS and Android store listings updated with new screenshots/changelog reflecting Phase 2 features; both submissions approved. | - Update store listing copy and screenshots for v1.5 - Submit and track both store review processes | iOS, Android | High | Low | Phase 2 — v1.5 (should-have follow-on release) | S27 (Weeks 53-54) | Ready
Sprint: S27 · Weeks 53-54 · Sprint Complexity: High · Gate: Phase 2 acceptance gate — RFP §6.1.2

## Jain Philosophy Module
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
PHIL-1 | As a member, I want a structured, multi-lesson educational module on anekantvad, ahimsa, syadvad, the Nine Tattvas, the Five Mahavratas, the Twelve Vratas, and karma theory, per RFP §4.3. | Curriculum is organized as sequential multi-lesson tracks per topic; a member can start, pause, and resume any track; content renders correctly with the diacritics/terminology rules from Phase 1. | - Build the curriculum content model and lesson-sequencing engine - Build the lesson-viewer UI with pause/resume - Populate the Nine Tattvas and Five Mahavratas tracks as the initial content set | iOS, Android, Web, Backend | Low | High | Phase 3 — v2.0 (nice-to-have and contingent) | S28-S29 (Weeks 55-58) | Ready
PHIL-2 | As a member, I want my progress tracked across lessons so I can see how far I've come in my study. | Progress bar per track and an overall completion percentage are visible; progress persists across sessions and devices for a signed-in member. | - Implement progress tracking per lesson and track - Sync progress across devices via the backend | iOS, Android, Web, Backend | Low | Medium | Phase 3 — v2.0 (nice-to-have and contingent) | S28-S29 (Weeks 55-58) | Ready
PHIL-3 | As an admin (curriculum author), I want curriculum authoring and lesson-sequencing tools plus progress analytics, per RFP §4.3. | Admin can author lessons, sequence them into tracks, and view aggregate progress analytics (completion rate per track, drop-off points). | - Build the curriculum authoring and sequencing UI - Build the progress-analytics dashboard | Admin, Backend | Low | Medium | Phase 3 — v2.0 (nice-to-have and contingent) | S28-S29 (Weeks 55-58) | Ready
Sprint: S28-S29 · Weeks 55-58 · Sprint Complexity: Medium · Gate: Sprint demo

## JCA Cares
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
CARES-1 | As a member, I want to see and give to JCA Cares campaigns (disaster relief, partner-organization fundraising, community outreach) so I can support causes beyond the Center itself, per RFP §4.3. | JCA Cares campaigns render using the existing Cause/Donate infrastructure with a distinct visual treatment and partner-organization attribution. | - Extend the Cause model to support external/partner-organization campaigns - Build the distinct JCA Cares visual treatment on the Donate tab | iOS, Android, Web, Backend | Low | Low | Phase 3 — v2.0 (nice-to-have and contingent) | S30 (Weeks 59-60) | Ready
CARES-2 | As an admin, I want campaign management integrated with the existing Causes tooling so JCA Cares doesn't require a parallel system, per RFP §4.3. | Admin manages JCA Cares campaigns through the same Causes & Donations section used for internal causes, with an added partner-organization field. | - Add the partner-organization field to the Cause admin editor - Verify JCA Cares campaigns report correctly in existing donation reports | Admin, Backend | Low | Low | Phase 3 — v2.0 (nice-to-have and contingent) | S30 (Weeks 59-60) | Ready
Sprint: S30 · Weeks 59-60 · Sprint Complexity: Low · Gate: Sprint demo

## v2.0 Hardening and Release
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
HARD2-1 | As JCA, I want a regression pass and updated pen-test scope for the v2.0 surface area (Jain Philosophy, JCA Cares) before release, per RFP §6.1.3. | Full regression suite passes across all surfaces; pen-test scope extended to cover the two new Phase 3 modules; High/Critical findings remediated. | - Run the full regression suite against the v2.0 build - Extend pen-test scope to Jain Philosophy and JCA Cares - Remediate and re-verify findings | Backend, Web, Admin, iOS, Android | High | Medium | Phase 3 — v2.0 (nice-to-have and contingent) | S31 (Weeks 61-62) | Ready
HARD2-2 | As the vendor, I want store updates for the v2.0 release submitted and approved on both stores, per RFP §6.1.3. | iOS and Android store listings updated reflecting v2.0 features; both submissions approved. | - Update store listing copy and screenshots for v2.0 - Submit and track both store review processes | iOS, Android | Medium | Low | Phase 3 — v2.0 (nice-to-have and contingent) | S31 (Weeks 61-62) | Ready
Sprint: S31 · Weeks 61-62 · Sprint Complexity: Medium · Gate: Phase 3 acceptance gate — RFP §6.1.3 (excludes AI Chat, which has its own gate)

## AI Chat
ID | User Story | Acceptance Criteria | Subtasks | Surfaces | Priority | Complexity | Phase | Sprint | Status
AI-C-1 | As the AI Chat team, I want a knowledge-base ingestion pipeline covering JCA institutional content, religious content, and FAQs so the chat has an accurate grounding corpus, per RFP §4.3. | Ingestion pipeline pulls from the Library/Jinvani catalog, FAQ, policies, and admin-curated source documents into a retrieval index; a content update in the source re-indexes within a defined SLA. | - Build the ingestion pipeline from existing content sources - Stand up the retrieval index (vector store) - Implement the re-indexing SLA on content update | Backend | Low | High | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 (AI Chat Wk 1-10 (parallel to Phase 3)) | Ready
AI-C-2 | As JCA's religious advisors, I want strict guardrails so the AI Chat never speculates on doctrine, always defers theological questions to acharyas, and cites sources for programming/factual claims, per RFP §4.3. | A doctrine-classification layer detects theological questions and returns a deferral response naming how to reach an acharya, never a generated theological answer; every factual/programming claim in a response includes a source citation; a red-team test set of doctrinal edge cases passes 100%. | - Build the doctrine-question classifier and deferral response - Implement mandatory source citation on factual claims - Build and run the red-team doctrinal edge-case test set with JCA religious advisors | Backend | Critical | Very High | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 (AI Chat Wk 1-10 (parallel to Phase 3)) | Ready
AI-C-3 | As a member, I want a chat interface on mobile and web so I can ask questions and get grounded answers or an escalation to staff, per RFP §4.3. | Chat UI available on iOS, Android, and web; every response is either grounded with a citation, a doctrine-deferral message, or an explicit hand-off to human staff — never an unlabeled guess. | - Build the chat UI on mobile and web - Wire the three response modes (grounded, deferral, hand-off) | iOS, Android, Web, Backend | Low | High | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 (AI Chat Wk 1-10 (parallel to Phase 3)) | Ready
AI-C-4 | As an admin, I want an escalation queue for sensitive topics and a response-audit tool so a human reviews what the AI actually says, per RFP §4.3. | Any hand-off from the chat lands in an admin escalation queue with the conversation context; admins can audit any past AI response and flag it for correction or knowledge-base update. | - Build the escalation queue in the admin utility - Build the response-audit tool with flagging | Admin, Backend | Low | Medium | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 (AI Chat Wk 1-10 (parallel to Phase 3)) | Ready
AI-C-5 | As an admin (knowledge-base curator), I want a curation UI and a user-feedback loop so the AI's grounding corpus improves over time, per RFP §4.3. | Admin can add, edit, or remove knowledge-base entries directly; a thumbs-up/down on any chat response feeds a feedback queue reviewed by the curator. | - Build the knowledge-base curation UI - Build the user-feedback capture and review queue | Admin, iOS, Android, Web, Backend | Low | Medium | Phase 3 — v2.0 (nice-to-have and contingent) | AI-1 to AI-5 (AI Chat Wk 1-10 (parallel to Phase 3)) | Ready
Sprint: AI-1 to AI-5 · AI Chat Wk 1-10 (parallel to Phase 3) · Sprint Complexity: Very High · Gate: AI Chat acceptance gate — separate commission per RFP §6.1.3 item 19